## Settings
Project |  |  | PreCon Start | 2018-08-15 | Contruction Start | 2019-01-13 |  | PTO Reimbursable | 2080
Location |  |  | PreCon Finish | 2019-01-13 | Construction Finish | 2020-06-22 |  | 4wks PTO Non-Reimbursable | 1760
Region | Boston |  | Duration | 5 | Duration | 17 |  | 3wks PTO Non-Reimbursable | 1840
Sector | Residential |  |  | 22 |  | 75 |  | SELECT | 2080
Ops Job # |  |  | Estimating LIT | 65% | Units |  | ea
Precon Task # |  |  | Construction LIT | 45% | Area |  | gsf
Date | 2018-08-09 12:51 |  | Precon Raises | 4%
|  |  | Construction Raises | 9% | Totals
Project Cost | 5000000 |  |  |  | Preconstruction | 0
|  |  | IT/week | 52 | Construction | 146965.6875
|  |  | Iphone/week | 35 | General Conditions | 0
Vacation | PTO Reimbursable |  | Gas/week | 120 | General Requirements | 0
| SECTORS | REGIONS
| Mixed-Use | Boston
| Parking | New York
| Office | Miami
| Retail | West Palm Beach
| Hospitality & Entertainment | Estero
| Residential | Tampa
| Elder Care | Dallas
| Health Care | San Diego
| Laboratory | Los Angeles
| Education | San Francisco
Community / Cultural
Sports / Recreation
Food Service
Manufacturing / Warehouse
Site / Infrastructure
Energy / Communications
Transportation
Government

## Staff Detail
[51 empty] | 2020-06-22 | 2019-01-13
2018-08-09 12:51
| PreCon Start | 2018-08-15 | Duration | 5 | IT/wk | 52 |  | Estimating LIT | 65%
| PreCon Finish | 2019-01-13 |  | 22 | Iphone/wk | 35 |  | Construction LIT | 45%
| Contruction Start | 2019-01-13 | Duration | 17 | Gas/wk | 120 |  | Precon Raises | 4%
| Construction Finish | 2020-06-22 |  | 75 |  |  |  | Construction Raises | 9%
1
|  |  |  | Annual Car Allow | Start Month |  | Start Date | Finish Date |  |  |  | 2018-08-13 | 2018-09-13 | 2018-10-13 | 2018-11-13 | 2018-12-13 | 2019-01-13 | 2019-02-13 | 2019-03-13 | 2019-04-13 | 2019-05-13 | 2019-06-13 | 2019-07-13 | 2019-08-13 | 2019-09-13 | 2019-10-13 | 2019-11-13 | 2019-12-13 | 2020-01-13 | 2020-02-13 | 2020-03-13 | 2020-04-13 | 2020-05-13 |  | Grand Total | Man Weeks | Sort Order | # of weeks | IT /week | IPhone /week | Gas /week | IT total | Iphone total | Gas total | Labor total | Total Annual | [6 empty] | 2018-12-13 | 2019-02-13
| Job Title | Name | Salary |  |  | Duration |  |  | % |  | -2 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | Rate | [13 empty] | Grand Total | staff ct | 2 |  |  | -1 | 2
| Precon | [6 empty] | graph staffing | [40 empty] | prelabor | 0
[8 empty] | Subtotals: |  |  | 0% | [23 empty] | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
| Construction | [8 empty] | 0 | 0 | [37 empty] | conlabor | 293931.3751
s | Safety Manager 2 |  | 135170 | 7200 | 1 | 17 | 2019-01-13 | 2020-06-22 | 10% | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 108.2495 | 34071.4744 | 7.5143 | 4.5 | 75.1429 | 52 | 35 | 120 | 390.7429 | 263 | 901.7143 | 32516.0173 | 225159.0321 |  | 34071.4744
s | Safety Manager 1 |  | 92050 |  | 1 | 17 | 2019-01-13 | 2020-06-22 | 50% | [7 empty] | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 70.0136 | 112894.2131 | 37.5714 | 4.6 | 75.1429 | 52 | 35 | 120 | 1953.7143 | 1315 | 4508.5714 | 105116.9274 | 145628.2721 |  | 112894.2131
[8 empty] | Subtotals: |  |  | 0% | [23 empty] | 146965.6875 | 45.0857 |  | 150.2857 | 52 | 35 | 120 | 2344.4571 | 1578 | 5410.2857 | 137632.9447 | 370787.3043 |  | 146965.6875
[5 empty] | -5 | 5 | 2018-08-15 | 2019-01-13 | [25 empty] | 0.2399 | 0 | 0 |  | 21.5714 | 52 | 35 | 120 | 0 | 0 | 0 | 0 | 498.9934 |  | 0
[5 empty] | 1 | 17 | 2019-01-13 | 2020-06-22 | [25 empty] | 0.068869 | 0 | 0 |  | 75.1429 | 52 | 35 | 120 | 0 | 0 | 0 | 0 | 143.2471 |  | 0
[34 empty] | 0 | 0 | 0 |  | 0 | 52 | 35 | 120 | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | -5 | 5 | 2018-08-15 | 2019-01-13 | [25 empty] | 0.2399 | 0 | 0 |  | 21.5714 | 52 | 35 | 120 | 0 | 0 | 0 | 0 | 498.9934 |  | 0
dp | New Phase: | [5 empty] | Start? | Finish? |  | 0 | 0
[8 empty] | Subtotals: | [26 empty] | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase Start |  | 0
Phase Finish

## LaborOLD (hidden)
|  | Labor |  |  |  | Safety |  |  |  | Police |  |  |  | Cleaning |  |  |  | Winter Cond |  |  |  | Fire Watch |  |  |  | Template
Index | Week | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total | Crew Size | Hours | Rates | Total
Subtotals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carry |  | 20% | 0 |  | 0 | 25% | 0 |  | 0 | 25% | 0 |  | 0 | 20% | 0 |  | 0 | 20% | 0 |  | 0 | 20% | 0 |  | 0 | 20% | 0 |  | 0
Totals
|  | Schedule Item | [6 empty] | Duration
1 | 1900-01-06 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Formulas:
Week = IFERROR(OFFSET([Week],-1,0)+7,Settings!\cstart)

## Labor Gantt
[6 empty] | 2019-01-20 |  |  |  | 2019-02-17 |  |  |  | 2019-03-17 |  |  |  | 2019-04-14 |  |  |  | 2019-05-12 | 2019-05-19 | 2019-05-26 | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 | 2019-07-21 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05
|  | Start Week | Duration | Pred | Lag | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 1
Add Phase Here:
|  | Start Week | Duration | % Work
| Construction | #NUM! | 0 | 0%
| Safety Manager 2 | 1 | 75.1429 | 10%
| Safety Manager 1 | 1 | 75.1429 | 50%
dp
labor gantt

## Non-Staff Labor
|  | Clean-Up Labor |  |  | Safety (C & L) |  |  | Police |  |  | Labor Steward |  |  | Carpenter Steward |  |  | Fire Watch |  |  | Template
Index | Week | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | Rate | OT | Total
1 | 2019-01-13 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
2 | 2019-01-20 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
3 | 2019-01-27 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
4 | 2019-02-03 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
5 | 2019-02-10 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
6 | 2019-02-17 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
7 | 2019-02-24 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
8 | 2019-03-03 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
9 | 2019-03-10 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
10 | 2019-03-17 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
11 | 2019-03-24 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
12 | 2019-03-31 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
13 | 2019-04-07 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
14 | 2019-04-14 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
15 | 2019-04-21 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
16 | 2019-04-28 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
17 | 2019-05-05 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
18 | 2019-05-12 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
19 | 2019-05-19 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
20 | 2019-05-26 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
21 | 2019-06-02 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
22 | 2019-06-09 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
23 | 2019-06-16 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
24 | 2019-06-23 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
25 | 2019-06-30 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
26 | 2019-07-07 | 1 | 20% | 5167.4832 | 5474.4624 | 25% | 27474635.4502 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
27 | 2019-07-14 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
28 | 2019-07-21 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
29 | 2019-07-28 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
30 | 2019-08-04 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
31 | 2019-08-11 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
32 | 2019-08-18 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
33 | 2019-08-25 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
34 | 2019-09-01 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
35 | 2019-09-08 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
36 | 2019-09-15 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
37 | 2019-09-22 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
38 | 2019-09-29 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
39 | 2019-10-06 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
40 | 2019-10-13 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
41 | 2019-10-20 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
42 | 2019-10-27 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
43 | 2019-11-03 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
44 | 2019-11-10 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
45 | 2019-11-17 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
46 | 2019-11-24 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
47 | 2019-12-01 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
48 | 2019-12-08 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
49 | 2019-12-15 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
50 | 2019-12-22 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
51 | 2019-12-29 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
52 | 2020-01-05 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
53 | 2020-01-12 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
54 | 2020-01-19 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
55 | 2020-01-26 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
56 | 2020-02-02 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
57 | 2020-02-09 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
58 | 2020-02-16 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
59 | 2020-02-23 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
60 | 2020-03-01 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
61 | 2020-03-08 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
62 | 2020-03-15 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
63 | 2020-03-22 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
64 | 2020-03-29 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
65 | 2020-04-05 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
66 | 2020-04-12 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
67 | 2020-04-19 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
68 | 2020-04-26 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
69 | 2020-05-03 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
70 | 2020-05-10 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
71 | 2020-05-17 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
72 | 2020-05-24 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
73 | 2020-05-31 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
74 | 2020-06-07 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
75 | 2020-06-14 | 1 | 20% | 5167.4832 | 5474.4624 |  | 27473042.1082 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Subtotals |  |  |  | 387561.24 | 410584.68 |  | 2060519585.004 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Foreman |  |  |  | 410584.68 |  |  | 449227.329
TOTALS |  |  |  | 798145.92 |  |  | 2060968812.333 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
1 | 1900-01-06 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Formulas:
Week = IFERROR(OFFSET([Week],-1,0)+7,Settings!\cstart)
non-staff labor

## Rate Tables
2019-06-02 | 4
Clean-Up Labor |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 103.02 | 130.8354 | 97.75 | 124.1425 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0
2018-12-01 | 101 | 128.27 | 99.25 | 126.0475 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0
2018-06-01 | 99.25 | 126.0475 | 101 | 128.27 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0
2017-12-01 | 97.75 | 124.1425 | 103.02 | 130.8354 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0
Laborer Foreman |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 109.14 | 138.6078 | 103.75 | 131.7625 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0
2018-12-01 | 107 | 135.89 | 105.5 | 133.985 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0
2018-06-01 | 105.5 | 133.985 | 107 | 135.89 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0
2017-12-01 | 103.75 | 131.7625 | 109.14 | 138.6078 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0
Safety & Carpentry |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 125.46 | 159.3342 | 118 | 149.86 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0
2018-09-01 | 123 | 156.21 | 120.5 | 153.035 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0
2018-03-01 | 120.5 | 153.035 | 123 | 156.21 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0
2017-09-01 | 118 | 149.86 | 125.46 | 159.3342 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0
Carpenter Foreman |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 134.895 | 171.3167 | 127.5 | 161.925 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0
2018-09-01 | 132.25 | 167.9575 | 130 | 165.1 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0
2018-03-01 | 130 | 165.1 | 132.25 | 167.9575 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0
2017-09-01 | 127.5 | 161.925 | 134.895 | 171.3167 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0
Police |  |  | Boston |  | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
0 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66
Labor Steward |  |  | Boston | 1.25 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-12-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-06-01 | 1 | 1.25 | 1 | 1.25 | 1.1 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0
2017-12-01 | 1 | 1.25 | 1 | 1.25 | 1.17 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0
Carpenter Steward |  |  | Boston | 1.25 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-09-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-03-01 | 1 | 1.25 | 1 | 1.25 | 1.1 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0
2017-09-01 | 1 | 1.25 | 1 | 1.25 | 1.17 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0
Fire Watch |  |  | Boston |  | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
0 | 45 | 66 | 45 | 66 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0

## GCs Detail
[8 empty] | regions | sectors | cost code
0
| Region: | Boston | weeks : | 75 | units : | 0
| Sector: | Residential | months : | 17 | area : | 0
| PROJECT STAFFING EXPENSES |  |  |  |  | 0 | [
| Weekly Parking Fees |  | 0 | wks | 300 | 0 | 1 |  |  | 982200
| Recruiting Charges |  | 0 | lsum | 0 | 0 | 1 |  |  | 982200
| Mileage |  | 0 | miles | 0.55 | 0 | 1 |  |  | 982200
| Airfare |  | 0 | flights | 0 | 0 | 1 |  |  | 982200
| TBD |  | 0 | nights | 0 | 0 | 1 |  |  | 982200
| Car Rental |  | 0 | days | 400 | 0 | 1 |  |  | 982200
| House/Apartment Rental |  | 0 | mos | 0 | 0 | 1 |  |  | 982200
| Moving/Relocation |  | 0 | mos | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982200
| Tolls |  | 0 | wks | 0 | 0 | 1 |  |  | 982200
| Food Allowance |  | 0 | wks | 0 | 0 | 1 |  |  | 982200
]
| PROJECT TRAILERS |  |  |  |  | 0 | [
1
]
| TEMPORARY OFFICE RENTAL |  |  |  |  | 0 | [
| Rental Fees |  | 0 | mos | 0 | 0 | 1 |  |  | 982300
| Build-Out Of Office Space |  | 0 | lsum | 0 | 0 | 1 |  |  | 982300
| Utilities |  | 0 | mos | 0 | 0 | 1 |  |  | 982300
| Demolition & Restore to Original Condition |  | 0 | lsum | 0 | 0 | 1 |  |  | 982300
]
| SUFFOLK OFFICE FUNITURE & EQUIPMENT |  |  |  |  | 0 | [
| Digital Camera |  | 0 | each | 500 | 0 | 1 |  |  | 982300
| Jobsite Live Streaming Camera - Earthcam |  | 0 | set-up | 12000 | 0 | 1 |  |  | 982300
| Jobsite Live Streaming Camera - Earthcam ($600/mth fee plus $300/mth for internet fee) |  | 0 | mos | 900 | 0 | 1 |  |  | 982300
| Cell Phone Charging Stations |  | 0 | each | 1250 | 0 | 1 |  |  | 982300
| Copiers |  | 0 | each | 2000 | 0 | 1 |  |  | 982300
| Copier Maintenance |  | 0 | each | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982300
| Office Supplies |  | 0 | mos | 350 | 0 | 1 |  |  | 982300
| Office Furniture for each staff member (Desks, Chairs, File Cabinet) |  | 0 | each | 600 | 0 | 1 |  |  | 982300
| Office Furniture (Conf. Tables, Chairs, Plan Tables, Filing Cabinets) |  | 0 | ls | 600 | 0 | 1 |  |  | 982300
| Consumables |  | 0 | mos | 200 | 0 | 1 |  |  | 982300
| Team Lunch (Owner Meetings) |  | 0 | mos | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982300
| Bottled Water/Coffee |  | 0 | mos | 250 | 0 | 1 |  |  | 982300
]
| INFORMATION TECHNOLOGY & SUPPORT |  |  |  |  | 0 | [
| Internet set-up / job site set up |  | 0 | lines | 1000 | 0 | 1 |  |  | 982300
| Internet Monthly Cost |  | 0 | mos | 0 |  | 1 |  |  | 982300
| Mifi Set-up Cost (Cradlepoints) |  | 0 | ea | 300 | 0 | 0 |  | Elder Care Laboratory Education Sports / Recreation | 982300
| Mifi Monthly Cost |  | 0 | mos | 265 | 0 | 1 |  |  | 982300
| Cisco PoE Switch (One required for every job) - Good for Up to 20 Users |  | 0 | each | 4600 | 0 | 1 |  |  | 982300
| Internal Wireless Access Point (Trailer) |  | 0 | ea | 600 | 0 | 0 | Tampa Dallas San Diego |  | 982300
| External Wireless Access Point (Site) |  | 0 | ea | 1820 | 0 | 1 | Boston San Diego Los Angeles San Francisco |  | 982300
| Cisco VoiP phone |  | 0 | each | 750 | 0 | 1 |  |  | 982300
| Cisco Conference Star phone |  | 0 | each | 1200 | 0 | 1 |  |  | 982300
| Red Analog Emergency Phone |  | 0 | each | 50 | 0 | 1 |  |  | 982300
| File Server, Rack, UPS, SkySync License |  | 0 | each | 25000 | 0 | 1 |  |  | 982300
]
| COMPUTER EQUIPMENT |  |  |  |  | 0 | [
| Printer |  | 0 | each | 450 | 0 | 1 |  |  | 982300
| Desktop Computer |  | 0 | each | 2265 | 0 | 1 |  |  | 982300
| Laptop Standard |  | 0 | each | 1500 | 0 | 1 |  |  | 982300
| Laptop BIM High Spec |  | 0 | each | 4500 | 0 | 1 |  |  | 982300
| 24" Monitor |  | 0 | each | 150 | 0 | 1 |  |  | 982300
| 27" Monitor |  | 0 | each | 150 | 0 | 1 |  |  | 982300
| 27" DELL 4K monitor |  | 0 | each | 450 | 0 | 1 |  |  | 982300
| Digital Signage |  | 0 | each | 2500 | 0 | 1 |  |  | 982300
| Microsoft Surface Hub |  | 0 | each | 1500 | 0 | 1 |  |  | 982300
| Apple TV (iPad Screen Mirroring) |  | 0 | each | 70 | 0 | 1 |  |  | 982300
| Field iPad |  | 0 | each | 860 | 0 | 1 |  |  | 982300
]
| PROCORE |  |  |  |  | 0 | [
| Procore Fee |  | 0 | contract | 0.07% | 0 | 1 |  |  | 982300
]
| SUFFOLK SAFETY APPLICATION |  |  |  |  | 0 | [
| Safety Application - per each on site staff |  | 0 | months | 65 | 0 | 1 |  |  | 982300
]
| BIM 360 |  |  |  |  | 0 | [
| BIM 360 |  | 0 | contract | 0.025% | 0 | 1 |  |  | 982300
]
| BIM |  |  |  |  | 0 | [
| Scanning an Existing Building |  | 0 | sf | 0.3 | 0 | 1 |  |  | 982300
| QA/QC of a New Building |  | 0 | sf | 0.6 | 0 | 1 |  |  | 982300
]
| LEAN CONSULTING |  |  |  |  | 0 | [
| Internal Consulting |  | 0 | months | 0 |  | 1 |  |  | 982400
| Touchplan Fees, Monthly |  | 0 | months | 0 |  | 1 |  |  | 982400
| Touchplan Fees, One Time Fee |  | 0 | ls | 0 |  | 1 |  |  | 982400
]
| MISCELLANEOUS EXPENSES |  |  |  |  | 0 | [
| Suffolk Project Sign |  | 0 | lsum | 5000 | 0 | 1 |  |  | 982400
| Marketing Photographs |  | 0 | lsum | 0 | 0 | 1 |  |  | 982400
| Aerial Photos |  | 0 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982400
| Client Entertainment |  | 0 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982400
| Topping Off Ceremony |  | 0 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982400
]
0
0
| Trailer | [8 empty] | 982300
| Rent |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Delivery |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Pick-up |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Aluminum Steps |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Security System |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Utility Connections |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Utility Consumption |  | 1 | lsum | 0 | 0 | 1 |  |  | 982300
| Skirting |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 982300
remove carry
prorate
catch all
Note on E60: Includes Microsoft Licensing
Note on E61: Includes Microsoft Licensing, keyboard, bag and docking station
Note on E62: Includes Microsoft Licensing, keyboard, bag and docking station

## GRs Detail
[8 empty] | regions | sectors | cost code
0
| Region: | Boston | weeks : | 75 | units : | 0
| Sector: | Residential | months : | 17 | area : | 0
| REPROGRAPHICS |  |  |  |  | 0 | [
| Pre-Construction |  | 0 | lsum | 250 | 0 | 1 |  |  | 011000
| Construction |  | 0 | mos | 600 | 0 | 1 |  |  | 011000
]
| POSTAGE & COURIER |  |  |  |  | 0 | [
| Pre-Construction |  | 2 | lsum |  | 0 | 1 |  |  | 011000
| Construction |  | 0 | lsum |  | 0 | 1 |  |  | 011000
]
| EXPLORITORY & SURVEYING SERVICES |  |  |  |  | 0 | [
| Exploratory Investigations |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Surveying Equipment |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Surveying Services |  | 0 | day | 1600 | 0 | 1 |  |  | 011000
| Survey Exist. Cond. / As-Builts |  | 0 | lsum |  | 0 | 1 |  |  | 011000
]
| PARKING SHUTTLES |  |  |  |  | 0 | [
| Rental of Offsite Parking Lot |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Parking Shuttle Van |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Parking Shuttle Van Driver |  | 0 | day | 280 | 0 | 1 |  |  | 011000
]
| CONSULTING SERVICES |  |  |  |  | 0 | [
| Consulting Services |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Legal Services |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011000
| Smoke Control |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011000
| Small Business/Work Force Compliance Consultant |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011000
| Lean Consulting Services |  | 0 | lsum |  | 0 | 1 |  |  | 011000
| Partnering Session |  | 0 | lsum |  | 0 | 0 |  | Elder Care Laboratory Education Sports / Recreation | 011000
]
| MISCELLANEOUS SUPPORT & EQUIPMENT |  |  |  |  | 0 | [
| Master Mechanic |  | 0 | wks | 6000 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 011000
| Teamster |  | 0 | wks | 5000 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 011000
| Trucking/Transportation |  | 0 | lsum | 0 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 011000
| Storage Trailer |  | 0 | mos | 165 | 0 | 1 |  |  | 011000
| Tools & Equipment |  | 0 | mos | 1000 | 0 | 1 |  |  | 011000
| Radios |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011000
| Rodent Control |  | 0 | mos | 300 | 0 | 1 |  |  | 011000
| Mock Ups (include removal) |  | 0 | lsum | 0 | 0 | 1 |  |  | 011000
| Off Hours Work Permit |  | 0 | days | 100 | 0 | 1 |  |  | 011000
| Punch List |  | 0 | lsum | 0 | 0 | 1 |  |  | 011000
| Cut & Patch |  | 0 | lsum | 0 | 0 | 1 |  |  | 011000
]
| WATER CONSUMPTION |  |  |  |  | 0 | [
| Water Consumption |  | 0 | lsum |  | 0 | 1 |  |  | 011100
]
| ELECTRICITY CONSUMPTION |  |  |  |  | 0 | [
| Electric Consumption |  | 0 | lsum |  | 0 | 1 |  |  | 011100
| Temp. Electric Vault & Service |  | 0 | months | 65 | 0 | 1 |  |  | 011100
]
| TEMPORARY TOILETS |  |  |  |  | 0 | [
| Portables |  | 0 | ea | 0 | 0 | 1 |  |  | 011100
| Portable Unit Delivery Fee |  | 0 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011100
| Temp Bathroom Install |  | 0 | ea | 100 | 0 | 1 |  |  | 011100
| Temp Bathroom Remove |  | 0 | ea | 100 | 0 | 1 |  |  | 011100
| Temp Bathroom Cleaning |  | 0 | lsum | 0 | 0 | 1 |  |  | 011100
| Hand Sanitizer |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011100
| Gel Pak |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011100
| Holding Tanks |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 011100
]
| CONSTRUCTION MANAGEMENT PLAN |  |  |  |  | 0 | [
| Police Details |  | 0 | lsum | 0 | 0 | 1 |  |  | 012100
| Sidewalk Bridge |  | 0 | lf | 175 | 0 | 1 |  |  | 012100
| New Traffic Markings |  | 0 | lsum |  | 0 | 1 |  |  | 012100
| Remove Old/Existing Traffic Markings |  | 0 | lsum |  | 0 | 1 |  |  | 012100
| Temporary Road Signs |  | 0 | lsum |  | 0 | 1 |  |  | 012100
| Sidewalk Rental |  | 0 | mos |  | 0 | 1 |  |  | 012100
| Street Rental |  | 0 | mos |  | 0 | 1 |  |  | 012100
| Railway Spotter |  | 0 | mos |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Car/Boat Detailing |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Clean Adjacent Building |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| MOT Plan |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Miscellaneous Permits |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Overtime Inspection Costs |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Access Point Turnstiles |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Hurricane Preparation |  | 0 | lsum |  | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 012100
| Parking Meter Fees |  | 0 | mos |  | 0 | 1 |  |  | 012100
| Off Hours Permit |  | 0 | lsum | 100 | 0 | 1 |  |  | 012100
]
| CONSTRUCTION FENCE |  |  |  |  | 0 | [
| Jersey Barriers |  | 0 | lf/month | 12 | 0 | 1 |  |  | 016100
| Fence on top of Jersey Barriers |  | 0 | lf | 10 | 0 | 1 |  |  | 016100
| Chain Link Fence |  | 0 | lf | 18 | 0 | 1 |  |  | 016100
| Windscreen/Scrim |  | 0 | lf | 18 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 016100
| Water Barriers |  | 0 | lf | 18 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 016100
| Gates |  | 0 | ea | 500 | 0 | 1 |  |  | 016100
| Maintenance & Relocations |  | 0 | wks | 0 | 0 | 1 |  |  | 016100
| Fence Removal |  | 0 | lf | 0 | 0 | 1 |  |  | 016100
| Laborer to Open & Close Gates |  | 0 | ls | 0 | 0 | 1 |  |  | 016100
]
| SAFETY SUPPLIES & EQUIPMENT |  |  |  |  | 0 | [
| Temporary Fire Extinguishers & Stands |  | 0 | ea | 200 | 0 | 1 |  |  | 012100
| Temporary Signage |  | 0 | lsum | 0 |  | 1 |  |  | 012100
| First Aid Supplies |  | 0 | mos | 0 |  | 1 |  |  | 012100
| Shanty Protection - smoke detector & fire extinguisher |  | 0 | ea | 200 |  | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 012100
| Shanty Portection - NYC Sprinkler Kit (not required yet - over 40 stories only) |  | 0 | ea | 750 |  | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 012100
| BFD Post (signage, gang box, keys, plans, etc. - over 40 stories only) |  | 0 | ea | 5000 |  | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 012100
| Creation of Temp. Fire Protection Plan (over 40 stories only) |  | 0 | ea | 25000 |  | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 012100
| Misc. Safety Supplies (hard hats, safety glasses, harnesses, etc) |  | 0 | mos | 0 | 0 | 1 |  |  | 012100
]
| SECURITY & WATCHES |  |  |  |  | 0 | [
| Fire Watch |  | 0 | lsum | 0 | 0 | 1 |  |  | 012100
| Security |  | 0 | hrs | 0 | 0 | 1 |  |  | 012100
]
| MISCELLANEOUS CLEANING |  |  |  |  | 0 | [
| Waste Management Plan |  | 0 | lsum | 2000 | 0 | 1 |  |  | 017400
| Final Cleaning - Building |  | 0 | sf | 0 | 0 | 1 |  |  | 017400
| Final Cleaning - Parking |  | 0 | sf | 0 | 0 | 1 |  |  | 017400
| Rubbish Chute |  | 0 | floors | 0 | 0 | 1 |  |  | 017400
]
| DUMPSTERS |  |  |  |  | 0 | [
| Dumpsters |  | 0 | loads |  | 0 | 1 |  |  | 017400
| Overweight Pulls (10% of total # of loads) |  | 0 | loads |  | 0 | 1 |  |  | 017400
]
| PERSONNEL & MATERIAL HOISTING |  |  |  |  | 0 | [
| Mobilize, Erect & Dismantle |  | 0 | lsum |  | 0 | 1 |  |  | 014100
| Police Details, Cranes, Permits during E & D |  | 0 | lsum |  |  | 1 |  |  | 014100
| Operating Engineers during E & D |  | 0 | lsum |  |  | 1 |  |  | 014100
| Hoist Rental (Single Car) |  | 0 | mos |  |  | 1 |  |  | 014100
| Hoist Rental (Double Car) |  | 0 | mos |  |  | 1 |  |  | 014100
| Gate Rental |  | 0 | mos |  |  | 1 |  |  | 014100
| Gate Installation |  | 0 | lsum |  |  | 0 | Miami West Palm Beach Estero Tampa |  | 014100
| Hoist Rental Insurance |  | 0 | lsum |  |  | 1 |  |  | 014100
| Communication Boxes |  | 0 | mos |  |  | 1 |  |  | 014100
| Jumps |  | 0 | ea |  |  | 1 |  |  | 014100
| Sales Tax |  | 0 | ea |  |  | 1 |  |  | 014100
| Operator Car #1 (Regular Time) |  | 0 | wks |  |  | 1 |  |  | 014100
| Operator Car #2 (Regular Time) |  | 0 | wks |  |  | 1 |  |  | 014100
| Operator Car #1 (Overtime) |  | 0 | wks |  |  | 1 |  |  | 014100
| Operator Car #2 (Overtime) |  | 0 | wks |  |  | 1 |  |  | 014100
| Temporary Interior Elevator Operator (Regular Time) |  | 0 | wks |  |  | 1 |  |  | 014100
| Temporary Interior Elevator Operator (Overtime) |  | 0 | wks |  |  | 1 |  |  | 014100
| Overtime Equipment Hours |  | 0 | lsum |  |  | 0 | Miami West Palm Beach Estero Tampa |  | 014100
| Elevator Maintenance |  | 0 | mos |  |  | 1 |  |  | 014100
| Elevator Repairs |  | 0 | lsum |  |  | 1 |  |  | 014100
| Drop Tests |  | 0 | lsum |  |  | 0 | Miami West Palm Beach Estero Tampa |  | 014100
| SCCI Costs: |  | 0 |  |  |  | 1
| Fence Enclosures |  | 0 | ea |  |  | 1 |  |  | 014100
| Concrete Pad |  | 0 | ea |  |  | 1 |  |  | 014100
| Reinforce Existing Structure @ Tie-Ins |  | 0 | ea |  |  | 1 |  |  | 014100
| Loading Docks/Ramps/Overhead Prot. |  | 0 | ea |  |  | 1 |  |  | 014100
| Cab Protection |  | 0 | lsum |  |  | 1 |  |  | 014100
| Plywood Partitions @ Gates |  | 0 | ea |  |  | 1 |  |  | 014100
| Temporary Power Consumption |  | 0 | ea |  |  | 1 |  |  | 014100
| Temporary Power Service |  | 0 | mos |  |  | 1 |  |  | 014100
| Threshold Rentals |  | 0 | mos |  |  | 1 |  |  | 014100
| Assist Crane |  | 0 | mos |  |  | 1 |  |  | 014100
| 3rd Party Certification |  | 0 | mos |  |  | 1 |  |  | 014100
]
| WINTER CONDITIONS / TEMPORARY HEAT |  |  |  |  | 0 | [
| Snow Removal from Building |  | 0 | lsum |  | 0 | 1 | Boston New York |  | 017100
| Snow Removal from Site |  | 0 | lsum |  | 0 | 1 | Boston New York |  | 017100
| Temporary Construction |  | 0 | lsum |  | 0 | 1 | Boston New York |  | 017100
| Miscellaneous Heat & Tarps |  | 0 | mos |  | 0 | 1 | Boston New York |  | 017100
| Portable Heaters |  | 0 | mos |  | 0 | 1 | Boston New York |  | 017100
| Babfar Rental/Install |  | 0 | mos |  | 0 | 1 | Boston New York |  | 017100
| Temp. Ductwork |  | 0 | lsum |  | 0 | 1 | Boston New York |  | 017100
| Use/cln perm.system |  | 0 | mos |  | 0 | 1 | Boston New York |  | 017100
| Labor |  | 0 | lsum | 0 | 0 | 1 | Boston New York |  | 017100
| Fuel |  | 0 | wks |  | 0 | 1 | Boston New York |  | 017100
]
| STAGING & SCAFFOLDING |  |  |  |  | 0 | [
| Exterior Scaffolding first months rental & dismantle |  | 0 | ea |  | 0 | 1 |  |  | 014100
| Exterior Scaffolding monthly rental |  | 0 | mos |  | 0 | 1 |  |  | 014100
| Exterior Scaffolding move planks |  | 0 | days |  | 0 | 1 |  |  | 014100
| Interior Scaffolding first months rental & dismantle |  | 0 | ea |  | 0 | 1 |  |  | 014100
| Interior Scaffolding monthly rental |  | 0 | mos |  | 0 | 1 |  |  | 014100
| Interior Scaffolding move planks |  | 0 | days |  | 0 | 1 |  |  | 014100
]
| TESTING & INSPECTIONS |  |  |  |  | 0 | [
| Soils |  | 0 | ea |  | 0 | 1 |  |  | 018100
| Concrete |  | 0 | ea |  | 0 | 1 |  |  | 018100
| Steel |  | 0 | ea |  | 0 | 1 |  |  | 018100
| Spray Fireproofing |  | 0 | ea |  | 0 | 1 |  |  | 018100
| Curtainwall & Windows |  | 0 | ea |  | 0 | 1 |  |  | 018100
]
| LABOR ITEMS |  |  |  |  | 0 | [
| Clean-Up Labor |  | 0 | lsum | 0 | 0 | 1
| Safety (C & L) |  | 0 | lsum | 0 | 0 | 1
| Police |  | 0 | lsum | 0 | 0 | 1
| Labor Steward |  | 0 | lsum | 0 | 0 | 1
| Carpenter Steward |  | 0 | lsum | 0 | 0 | 1
| Fire Watch |  | 0 | lsum | 0 | 0 | 1
]
0
0
|  |  | 1 | lsum |  | 0 | 1
remove carry
prorate
catch all
Note on E38: Includes Microsoft Licensing
Note on E39: Includes Microsoft Licensing, keyboard, bag and docking station
Note on E40: Includes Microsoft Licensing, keyboard, bag and docking station

## GCs Owner
0
General Conditions
2018-08-09 12:51
|  | Project Staffing: |  | % of Time | Bill Rate | QT | Unit | Total
|  | Precon | 0 | 0% | 0 | 0 | wks | 0
|  | Construction | 0 | 0% | 0 | 0 | wks | 0
|  | Safety Manager 2 | 0 | 10% | 108.2495 | 7.5143 | wks | 813.4179
|  | Safety Manager 1 | 0 | 50% | 70.0136 | 37.5714 | wks | 2630.5107
0
|  | SUBTOTAL | [5 empty] | 3443.9286
|  | PROJECT STAFFING EXPENSES |  |  | 0% | 0 | 0 | 0
|  | Weekly Parking Fees |  |  | 300 | 0 | wks | 0
|  | Recruiting Charges |  |  | 0 | 0 | lsum | 0
|  | Mileage |  |  | 0.55 | 0 | miles | 0
|  | Airfare |  |  | 0 | 0 | flights | 0
|  | TBD |  |  | 0 | 0 | nights | 0
|  | Car Rental |  |  | 400 | 0 | days | 0
|  | House/Apartment Rental |  |  | 0 | 0 | mos | 0
|  | Moving/Relocation |  |  | 0 | 0 | mos | 0
|  | Tolls |  |  | 0 | 0 | wks | 0
|  | Food Allowance |  |  | 0 | 0 | wks | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | PROJECT TRAILERS |  |  | 0% | 0 | 0 | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | TEMPORARY OFFICE RENTAL |  |  | 0% | 0 | 0 | 0
|  | Rental Fees |  |  | 0 | 0 | mos | 0
|  | Build-Out Of Office Space |  |  | 0 | 0 | lsum | 0
|  | Utilities |  |  | 0 | 0 | mos | 0
|  | Demolition & Restore to Original Condition |  |  | 0 | 0 | lsum | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | SUFFOLK OFFICE FUNITURE & EQUIPMENT |  |  | 0% | 0 | 0 | 0
|  | Digital Camera |  |  | 500 | 0 | each | 0
|  | Jobsite Live Streaming Camera - Earthcam |  |  | 12000 | 0 | set-up | 0
|  | Jobsite Live Streaming Camera - Earthcam ($600/mth fee plus $300/mth for internet fee) |  |  | 900 | 0 | mos | 0
|  | Cell Phone Charging Stations |  |  | 1250 | 0 | each | 0
|  | Copiers |  |  | 2000 | 0 | each | 0
|  | Copier Maintenance |  |  | 0 | 0 | each | 0
|  | Office Supplies |  |  | 350 | 0 | mos | 0
|  | Office Furniture for each staff member (Desks, Chairs, File Cabinet) |  |  | 600 | 0 | each | 0
|  | Office Furniture (Conf. Tables, Chairs, Plan Tables, Filing Cabinets) |  |  | 600 | 0 | ls | 0
|  | Consumables |  |  | 200 | 0 | mos | 0
|  | Team Lunch (Owner Meetings) |  |  | 0 | 0 | mos | 0
|  | Bottled Water/Coffee |  |  | 250 | 0 | mos | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | INFORMATION TECHNOLOGY & SUPPORT |  |  | 0% | 0 | 0 | 0
|  | Internet set-up / job site set up |  |  | 1000 | 0 | lines | 0
|  | Internet Monthly Cost |  |  | 0 | 0 | mos | 0
|  | Mifi Set-up Cost (Cradlepoints) |  |  | 300 | 0 | ea | 0
|  | Mifi Monthly Cost |  |  | 265 | 0 | mos | 0
|  | Cisco PoE Switch (One required for every job) - Good for Up to 20 Users |  |  | 4600 | 0 | each | 0
|  | Internal Wireless Access Point (Trailer) |  |  | 600 | 0 | ea | 0
|  | External Wireless Access Point (Site) |  |  | 1820 | 0 | ea | 0
|  | Cisco VoiP phone |  |  | 750 | 0 | each | 0
|  | Cisco Conference Star phone |  |  | 1200 | 0 | each | 0
|  | Red Analog Emergency Phone |  |  | 50 | 0 | each | 0
|  | File Server, Rack, UPS, SkySync License |  |  | 25000 | 0 | each | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | COMPUTER EQUIPMENT |  |  | 0% | 0 | 0 | 0
|  | Printer |  |  | 450 | 0 | each | 0
|  | Desktop Computer |  |  | 2265 | 0 | each | 0
|  | Laptop Standard |  |  | 1500 | 0 | each | 0
|  | Laptop BIM High Spec |  |  | 4500 | 0 | each | 0
|  | 24" Monitor |  |  | 150 | 0 | each | 0
|  | 27" Monitor |  |  | 150 | 0 | each | 0
|  | 27" DELL 4K monitor |  |  | 450 | 0 | each | 0
|  | Digital Signage |  |  | 2500 | 0 | each | 0
|  | Microsoft Surface Hub |  |  | 1500 | 0 | each | 0
|  | Apple TV (iPad Screen Mirroring) |  |  | 70 | 0 | each | 0
|  | Field iPad |  |  | 860 | 0 | each | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | PROCORE |  |  | 0% | 0 | 0 | 0
|  | Procore Fee |  |  | 0.0007 | 0 | contract | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | SUFFOLK SAFETY APPLICATION |  |  | 0% | 0 | 0 | 0
|  | Safety Application - per each on site staff |  |  | 65 | 0 | months | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | BIM 360 |  |  | 0% | 0 | 0 | 0
|  | BIM 360 |  |  | 0.00025 | 0 | contract | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | BIM |  |  | 0% | 0 | 0 | 0
|  | Scanning an Existing Building |  |  | 0.3 | 0 | sf | 0
|  | QA/QC of a New Building |  |  | 0.6 | 0 | sf | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | LEAN CONSULTING |  |  | 0% | 0 | 0 | 0
|  | Internal Consulting |  |  | 0 | 0 | months | 0
|  | Touchplan Fees, Monthly |  |  | 0 | 0 | months | 0
|  | Touchplan Fees, One Time Fee |  |  | 0 | 0 | ls | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | MISCELLANEOUS EXPENSES |  |  | 0% | 0 | 0 | 0
|  | Suffolk Project Sign |  |  | 5000 | 0 | lsum | 0
|  | Marketing Photographs |  |  | 0 | 0 | lsum | 0
|  | Aerial Photos |  |  | 0 | 0 | lsum | 0
|  | Client Entertainment |  |  | 0 | 0 | lsum | 0
|  | Topping Off Ceremony |  |  | 0 | 0 | lsum | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | GENERAL CONDITIONS TOTAL | [5 empty] | 0
[7 empty] | Missing | 0
Don't Forget to relocate the items below that were transferred from the GRs up into the GCs
Line Item
Header
#REF!
#REF!
#REF!
#REF!
#REF! |  | Cisco VoiP phone |  |  | #REF! | #REF! | #REF! | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | wks | #REF!
#REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | wks | #REF!
Phase Item
`
move on page
add blank row
delete
add line item
add header
move to GRs
  Restore Defaults
  Toggle Names
  Button Three
  Button Four

## GRs Owner
0
General Requirements
2018-08-09 12:51
|  | Value | QT | Unit | TOTAL
| REPROGRAPHICS | 0% | 0 | 0 | 0
| Pre-Construction | 250 | 0 | lsum | 0
| Construction | 600 | 0 | mos | 0
| 0 | 0% | 0 | 0 | 0
| POSTAGE & COURIER | 0% | 0 | 0 | 0
| Pre-Construction | 0 | 2 | lsum | 0
| Construction | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| EXPLORITORY & SURVEYING SERVICES | 0% | 0 | 0 | 0
| Exploratory Investigations | 0 | 0 | lsum | 0
| Surveying Equipment | 0 | 0 | lsum | 0
| Surveying Services | 1600 | 0 | day | 0
| Survey Exist. Cond. / As-Builts | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| PARKING SHUTTLES | 0% | 0 | 0 | 0
| Rental of Offsite Parking Lot | 0 | 0 | lsum | 0
| Parking Shuttle Van | 0 | 0 | lsum | 0
| Parking Shuttle Van Driver | 280 | 0 | day | 0
| 0 | 0% | 0 | 0 | 0
| CONSULTING SERVICES | 0% | 0 | 0 | 0
| Consulting Services | 0 | 0 | lsum | 0
| Legal Services | 0 | 0 | lsum | 0
| Smoke Control | 0 | 0 | lsum | 0
| Small Business/Work Force Compliance Consultant | 0 | 0 | lsum | 0
| Lean Consulting Services | 0 | 0 | lsum | 0
| Partnering Session | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| MISCELLANEOUS SUPPORT & EQUIPMENT | 0% | 0 | 0 | 0
| Master Mechanic | 6000 | 0 | wks | 0
| Teamster | 5000 | 0 | wks | 0
| Trucking/Transportation | 0 | 0 | lsum | 0
| Storage Trailer | 165 | 0 | mos | 0
| Tools & Equipment | 1000 | 0 | mos | 0
| Radios | 0 | 0 | ea | 0
| Rodent Control | 300 | 0 | mos | 0
| Mock Ups (include removal) | 0 | 0 | lsum | 0
| Off Hours Work Permit | 100 | 0 | days | 0
| Punch List | 0 | 0 | lsum | 0
| Cut & Patch | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| WATER CONSUMPTION | 0% | 0 | 0 | 0
| Water Consumption | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| ELECTRICITY CONSUMPTION | 0% | 0 | 0 | 0
| Electric Consumption | 0 | 0 | lsum | 0
| Temp. Electric Vault & Service | 65 | 0 | months | 0
| 0 | 0% | 0 | 0 | 0
| TEMPORARY TOILETS | 0% | 0 | 0 | 0
| Portables | 0 | 0 | ea | 0
| Portable Unit Delivery Fee | 0 | 0 | lsum | 0
| Temp Bathroom Install | 100 | 0 | ea | 0
| Temp Bathroom Remove | 100 | 0 | ea | 0
| Temp Bathroom Cleaning | 0 | 0 | lsum | 0
| Hand Sanitizer | 0 | 0 | ea | 0
| Gel Pak | 0 | 0 | ea | 0
| Holding Tanks | 0 | 0 | ea | 0
| 0 | 0% | 0 | 0 | 0
| CONSTRUCTION MANAGEMENT PLAN | 0% | 0 | 0 | 0
| Police Details | 0 | 0 | lsum | 0
| Sidewalk Bridge | 175 | 0 | lf | 0
| New Traffic Markings | 0 | 0 | lsum | 0
| Remove Old/Existing Traffic Markings | 0 | 0 | lsum | 0
| Temporary Road Signs | 0 | 0 | lsum | 0
| Sidewalk Rental | 0 | 0 | mos | 0
| Street Rental | 0 | 0 | mos | 0
| Railway Spotter | 0 | 0 | mos | 0
| Car/Boat Detailing | 0 | 0 | lsum | 0
| Clean Adjacent Building | 0 | 0 | lsum | 0
| MOT Plan | 0 | 0 | lsum | 0
| Miscellaneous Permits | 0 | 0 | lsum | 0
| Overtime Inspection Costs | 0 | 0 | lsum | 0
| Access Point Turnstiles | 0 | 0 | lsum | 0
| Hurricane Preparation | 0 | 0 | lsum | 0
| Parking Meter Fees | 0 | 0 | mos | 0
| Off Hours Permit | 100 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| CONSTRUCTION FENCE | 0% | 0 | 0 | 0
| Jersey Barriers | 12 | 0 | lf/month | 0
| Fence on top of Jersey Barriers | 10 | 0 | lf | 0
| Chain Link Fence | 18 | 0 | lf | 0
| Windscreen/Scrim | 18 | 0 | lf | 0
| Water Barriers | 18 | 0 | lf | 0
| Gates | 500 | 0 | ea | 0
| Maintenance & Relocations | 0 | 0 | wks | 0
| Fence Removal | 0 | 0 | lf | 0
| Laborer to Open & Close Gates | 0 | 0 | ls | 0
| 0 | 0% | 0 | 0 | 0
| SAFETY SUPPLIES & EQUIPMENT | 0% | 0 | 0 | 0
| Temporary Fire Extinguishers & Stands | 200 | 0 | ea | 0
| Temporary Signage | 0 | 0 | lsum | 0
| First Aid Supplies | 0 | 0 | mos | 0
| Shanty Protection - smoke detector & fire extinguisher | 200 | 0 | ea | 0
| Shanty Portection - NYC Sprinkler Kit (not required yet - over 40 stories only) | 750 | 0 | ea | 0
| BFD Post (signage, gang box, keys, plans, etc. - over 40 stories only) | 5000 | 0 | ea | 0
| Creation of Temp. Fire Protection Plan (over 40 stories only) | 25000 | 0 | ea | 0
| Misc. Safety Supplies (hard hats, safety glasses, harnesses, etc) | 0 | 0 | mos | 0
| 0 | 0% | 0 | 0 | 0
| SECURITY & WATCHES | 0% | 0 | 0 | 0
| Fire Watch | 0 | 0 | lsum | 0
| Security | 0 | 0 | hrs | 0
| 0 | 0% | 0 | 0 | 0
| MISCELLANEOUS CLEANING | 0% | 0 | 0 | 0
| Waste Management Plan | 2000 | 0 | lsum | 0
| Final Cleaning - Building | 0 | 0 | sf | 0
| Final Cleaning - Parking | 0 | 0 | sf | 0
| Rubbish Chute | 0 | 0 | floors | 0
| 0 | 0% | 0 | 0 | 0
| DUMPSTERS | 0% | 0 | 0 | 0
| Dumpsters | 0 | 0 | loads | 0
| Overweight Pulls (10% of total # of loads) | 0 | 0 | loads | 0
| 0 | 0% | 0 | 0 | 0
| PERSONNEL & MATERIAL HOISTING | 0% | 0 | 0 | 0
| Mobilize, Erect & Dismantle | 0 | 0 | lsum | 0
| Police Details, Cranes, Permits during E & D | 0 | 0 | lsum | 0
| Operating Engineers during E & D | 0 | 0 | lsum | 0
| Hoist Rental (Single Car) | 0 | 0 | mos | 0
| Hoist Rental (Double Car) | 0 | 0 | mos | 0
| Gate Rental | 0 | 0 | mos | 0
| Gate Installation | 0 | 0 | lsum | 0
| Hoist Rental Insurance | 0 | 0 | lsum | 0
| Communication Boxes | 0 | 0 | mos | 0
| Jumps | 0 | 0 | ea | 0
| Sales Tax | 0 | 0 | ea | 0
| Operator Car #1 (Regular Time) | 0 | 0 | wks | 0
| Operator Car #2 (Regular Time) | 0 | 0 | wks | 0
| Operator Car #1 (Overtime) | 0 | 0 | wks | 0
| Operator Car #2 (Overtime) | 0 | 0 | wks | 0
| Temporary Interior Elevator Operator (Regular Time) | 0 | 0 | wks | 0
| Temporary Interior Elevator Operator (Overtime) | 0 | 0 | wks | 0
| Overtime Equipment Hours | 0 | 0 | lsum | 0
| Elevator Maintenance | 0 | 0 | mos | 0
| Elevator Repairs | 0 | 0 | lsum | 0
| Drop Tests | 0 | 0 | lsum | 0
| SCCI Costs: | 0 | 0 | 0 | 0
| Fence Enclosures | 0 | 0 | ea | 0
| Concrete Pad | 0 | 0 | ea | 0
| Reinforce Existing Structure @ Tie-Ins | 0 | 0 | ea | 0
| Loading Docks/Ramps/Overhead Prot. | 0 | 0 | ea | 0
| Cab Protection | 0 | 0 | lsum | 0
| Plywood Partitions @ Gates | 0 | 0 | ea | 0
| Temporary Power Consumption | 0 | 0 | ea | 0
| Temporary Power Service | 0 | 0 | mos | 0
| Threshold Rentals | 0 | 0 | mos | 0
| Assist Crane | 0 | 0 | mos | 0
| 3rd Party Certification | 0 | 0 | mos | 0
| 0 | 0% | 0 | 0 | 0
| WINTER CONDITIONS / TEMPORARY HEAT | 0% | 0 | 0 | 0
| Snow Removal from Building | 0 | 0 | lsum | 0
| Snow Removal from Site | 0 | 0 | lsum | 0
| Temporary Construction | 0 | 0 | lsum | 0
| Miscellaneous Heat & Tarps | 0 | 0 | mos | 0
| Portable Heaters | 0 | 0 | mos | 0
| Babfar Rental/Install | 0 | 0 | mos | 0
| Temp. Ductwork | 0 | 0 | lsum | 0
| Use/cln perm.system | 0 | 0 | mos | 0
| Labor | 0 | 0 | lsum | 0
| Fuel | 0 | 0 | wks | 0
| 0 | 0% | 0 | 0 | 0
| STAGING & SCAFFOLDING | 0% | 0 | 0 | 0
| Exterior Scaffolding first months rental & dismantle | 0 | 0 | ea | 0
| Exterior Scaffolding monthly rental | 0 | 0 | mos | 0
| Exterior Scaffolding move planks | 0 | 0 | days | 0
| Interior Scaffolding first months rental & dismantle | 0 | 0 | ea | 0
| Interior Scaffolding monthly rental | 0 | 0 | mos | 0
| Interior Scaffolding move planks | 0 | 0 | days | 0
| 0 | 0% | 0 | 0 | 0
| TESTING & INSPECTIONS | 0% | 0 | 0 | 0
| Soils | 0 | 0 | ea | 0
| Concrete | 0 | 0 | ea | 0
| Steel | 0 | 0 | ea | 0
| Spray Fireproofing | 0 | 0 | ea | 0
| Curtainwall & Windows | 0 | 0 | ea | 0
| 0 | 0% | 0 | 0 | 0
| LABOR ITEMS | 0% | 0 | 0 | 0
| Clean-Up Labor | 0 | 0 | lsum | 0
| Safety (C & L) | 0 | 0 | lsum | 0
| Police | 0 | 0 | lsum | 0
| Labor Steward | 0 | 0 | lsum | 0
| Carpenter Steward | 0 | 0 | lsum | 0
| Fire Watch | 0 | 0 | lsum | 0
| 0 | 0% | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0
| GENERAL REQUIREMENTS TOTAL |  |  |  | 0
|  |  |  | Missing | 0
Don't Forget to relocate the items below that were transferred from the GRs up into the GCs
Line Item
Header
move on page
add blank row
delete
add line item
add header
move to GCs
`
  Restore Defaults
  Button Two
  Button Three
  Button Four

## Bin (hidden)
CLEANING & MISC. LABOR |  |  |  | 0 | [
Clean-up Laborers | 1 | lsum | 0 | 0 | 1
Laborers |  | lsum |  | 0 | 1
Materials |  | mos |  | 0 | 1
Cleaning Supplies |  | wks |  | 0 | 1
Cleaning Site |  | hrs |  | 0 | 1
Cleaning Trailers/Office | 1 | hrs | 0 | 0 | 1
TEMPORARY SAFETY & PROTECTION |  |  |  | 0 | [
Carpenters | 1 | lsum |  | 0 | 1
Laborers | 1 | lsum | 0 | 0 | 1
Materials |  | lsum | 0 | 0 | 1
Stair Towers during excavation of foundation |  | ea | 0 | 0 | 1
1

## Errors
USERNAME | MODULE | PROCEDURE | MESSAGE | NUMBER | TIME
CAjoku ScheduleMod RemoveMergeSection Object variable or With block variable not set 91 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:01 PM CAjoku GanttMod recordState Type mismatch 13 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:02 PM CAjoku ScheduleMod RemoveMergeSection Object variable or With block variable not set 91 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:06 PM CAjoku GanttMod recordState Type mismatch 13 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:06 PM CAjoku ScheduleMod RemoveMergeSection Object variable or With block variable not set 91 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:07 PM CAjoku GanttMod recordState Type mismatch 13 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:08 PM CAjoku ScheduleMod RemoveMergeSection Object variable or With block variable not set 91 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:09 PM CAjoku GanttMod recordState Type mismatch 13 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:10 PM CAjoku ScheduleMod RemoveMergeSection Object variable or With block variable not set 91 GCGR_CodeNEWPENDING.xlsm 8/7/2018 3:13:11 PM

## Code
| \position | \rank | \order | \salary | \auto | \revit | \id |  | copiers |  |  | institutional BIM |  |  | Commercial BIM |  |  | Trailers
| Position | Rank | Insert Order | Salary Default | Auto | Tokens/wk | ID |  | if >= | then |  | if >= | then |  | if >= | then |  |  | (60 x 12) Single-wide trailer | (64 x 24) Double-wide trailer | (64 x 36) Triple-wide trailer |  | Trailer Table
| VP Of Operations | 6 | 1.2 | 336200 | 12000 | 0 |  |  | 0 | 2000 |  | 0 | 0 |  | 0 | 0 |  | Rent | 400 | 1125 | 2450 |  | (60 x 12) Single-wide trailer
| Project Executive 3 | 4 | 1.25 | [5 empty] | 5 | 7500 |  | 3000000 | 10000 |  | 3000000 | 10000 |  | Delivery | 7700 | 21500 | 28500 |  | (64 x 24) Double-wide trailer
| Project Executive 2 | 4 | 1.3 | 277840 | 9000 | 2 |  |  | 10 | 12500 |  | 10000000 | 40000 |  | 10000000 | 50000 |  | Pick-up | 5000 | 16500 | 21000 |  | (64 x 36) Triple-wide trailer
| Project Executive 1 | 4 | 1.4 | 215860 | 8000 | 2 | [5 empty] | 50000000 | 100000 |  | 50000000 | 220000 |  | Aluminum Steps | 50 | 50 | 50
| Sr. Project Manager 2 | 1 | 1.5 | 201170 | 7200 | 2 | [5 empty] | 150000000 | 200000 |  | 250000000 | 380000 |  | Security System | 50 | 50 | 50
| Sr. Project Manager 1 | 4 | 1.6 | 165570 | 6800 | 2 |  |  | internet |  |  | 300000000 | 400000 |  | 450000000 | 550000 |  | Utility Connections | 2000 | 2000 | 2000
| Project Manager 2 | 4 | 2.2 | 154810 | 6000 | 0 |  |  | if >= | then | [7 empty] | Utility Consumption | 100 | 200 | 300
| Project Manager 1 | 10 | 2.2 | 115240 | 6000 | 0 |  |  | 0 | 800 | [7 empty] | Skirting
| Asst Project Manager 1 | 10 | 2.3 | 77210 |  | 2 |  |  | 5 | 1600
| Asst Project Manager 2 | 2 | 2.4 | 95800 |  | 3 |  |  | 15 | 2000
| Project Engineer | 2 | 2.5 | 70000 |  | 5
| Proj Admin | 5 | 2.6 | 62750 |  | 5
| General Superintendent | 3 | 2.7 | 348880 | 12000 | 3 |  |  | Internal Consulting |  |  | touchplan fees | [5 empty] | Labor |  |  |  |  | Schedule Table
| Sr. Superintendent 3 | 10 | 2.8 | 286640 | 9000 | 3 |  |  | if >= | then |  | if >= | monthly | one time |  |  |  | if >= | Straight | 1-1/2X | 2X |  | Boston | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Sr. Superintendent 2 | 5 | 2.9 | 226300 | 8000 | 0 |  |  | 0 | 0 |  | 0 | 550 | 1000 |  |  | 2019-01-13 | 2019-01-13 |  |  |  |  | New York | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Sr. Superintendent 1 | 2 | 3.2 | 185620 | 7200 | 0 |  |  | 5000000 | 250 |  | 10000000 | 750 | 1500 |  |  |  | 2019-07-14 |  |  |  |  | Miami | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 3 | 4 | 3.3 | 181330 | 7200 | 0 |  |  | 25000000 | 400 |  | 100000000 | 1250 | 2500 |  |  |  | 2020-01-12 |  |  |  |  | West Palm Beach | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 2 | 7 | 3.4 | 151260 | 6000 | 0 |  |  | 100000000 | 600 | [7 empty] | 2020-07-12 |  |  |  |  | Estero | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 1 | 8 | 4.1 | 122400 | 6000 | 0 | [11 empty] | 2021-01-10 |  |  |  |  | Tampa | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Asst Superintendent 2 | 9 | 4.2 | 95200 |  | 0 | [11 empty] | 2021-07-11 |  |  |  |  | Dallas | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Asst Superintendent 1 |  | 4.3 | 80420 | [13 empty] | 2022-01-09 |  |  |  |  | San Diego | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| MEP Superintendent |  | 4.35 | [19 empty] | Los Angeles | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| Director Of Field Ops |  | 4.38 | [19 empty] | San Francisco | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| Field Engineer |  | 4.4 | 70000
| Senior Safety Manager 1 |  | 4.45 | [8 empty] | 50000
| Safety Manager 2 |  | 4.5 | 135170 | 7200 | [10 empty] | (60 x 12) Single-wide trailer |  |  | 400
| Safety Manager 1 |  | 4.6 | 92050 | [11 empty] | Rent
| Reg Safety Director |  | 4.7 | 175090 | 7200 | [6 empty] | 10000000
| Scheduling Director (601) |  | 4.8 | 233970
| Senior Scheduler |  | 4.9 | 160100
| Scheduler |  | 5 | 96760 | [12 empty] | Laborer
| Junior Scheduler |  | 5.05 | [14 empty] | Boston | New York | Miami | West Palm Beach | Estero | Tampa | Dallas | San Diego | Los Angeles | San Francisco
| VP Engineering |  | 5.1 | 297030 | 12000 | [9 empty] | OT Ratio: 1.27 |  | 2018-06-01 | 99.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Sr. MEP Project Manager |  | 5.2 | 202150 | 8000 | [9 empty] | DT Ratio: 1.5 |  | 2018-12-01 | 1.054 | 1.1 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
| MEP Project Manager |  | 5.3 | 154020 | [12 empty] | 2019-06-01 | 1.09 | 1.17 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Reg. BIM/VDC Director |  | 5.4 | 200000 | 7200
| VDC Manager |  | 5.5 | 130540
| VDC Coordinator |  | 5.6 | 77730
| Director of Trade Partner Diversity |  | 5.7 | 149760
| Trade Partner Diversity Officer |  | 5.8 | 68660
| Project Controller |  | 5.9 | 129280
| Project Accountant |  | 6 | 68450
| VP of Preconstruction |  | 6.1 | 360850 | 12000
\est | Chief Estimator |  | 6.15 |  |  |  | est
\est | Sr. Estimator 2 |  | 6.2 | 259220 |  |  | est
\est | Sr. Estimator 1 |  | 6.3 | 197980 |  |  | est
\est | MEP Estimator |  | 6.4 | 211440 |  |  | est
\est | Estimator 2 |  | 6.5 | 150790 |  |  | est
\est | Estimator 1 |  | 6.55 |  |  |  | est
\est | Estimating Manager |  | 6.57 |  |  |  | est
\est | Assistant Estimator |  | 6.6 | 85430 |  |  | est
\est | Estimating Assistant |  | 6.7 | 75920 |  |  | est
\est | Career Start Estimator |  | 6.9 | 70000 |  |  | est
| Intern |  | 7
| Safety Presets | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| if >= | Boston | New York | Miami | West Palm Beach | Estero | Tampa | Dallas | San Diego | Los Angeles | San Francisco
| 0 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 |  |  |  |  | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1
| 5000000 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1
| 40000000 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 |  |  |  |  | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2
| 150000000 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 |  |  |  |  | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35

## CostCodes
Code | Cost Code Description | MF3 | Map Description
010000.000 | General Requirements | 10000 | General Requirements
010100.010 | Document Reproduction | 10000 | Document Reproduction
010100.015 | Postage and Courier | 10000 | Postage and Courier
010100.020 | Exploratory Investigations | 10000 | Exploratory Investigations
010100.030 | Surveying Equipment | 10000 | Surveying Equipment
010100.040 | Surveying Services | 10000 | Surveying Services
010100.050 | Survey Exist. Cond. / As-Builts | 10000 | Survey Exist. Cond. / As-Builts
010100.060 | Parking Shuttle Van | 10000 | Parking Shuttle Van
010100.070 | Parking Shuttle Van Driver | 10000 | Parking Shuttle Van Driver
010100.080 | Consulting Services | 10000 | Consulting Services
010100.090 | Partnering Sessions | 10000 | Partnering Sessions
010100.100 | Entertainment / Topping Off / Etc. | 10000 | Entertainment / Topping Off / Etc.
010100.110 | Master Mechanic | 10000 | Master Mechanic
010100.120 | Teamster | 10000 | Teamster
010100.130 | Trucking/Transportation | 10000 | Trucking/Transportation
010100.140 | On Site Vehicle | 10000 | On Site Vehicle
010100.150 | Storage Trailer | 10000 | Storage Trailer
010100.160 | Tools and Equipment | 10000 | Tools and Equipment
010100.170 | Rodent Control | 10000 | Rodent Control
010100.180 | Mock Ups (include removal) | 10000 | Mock Ups (include removal)
010100.190 | Punch List | 10000 | Punch List
010100.200 | Cut and Patch | 10000 | Cut and Patch
010100.210 | Signage | 10000 | Signage
010100.215 | Digital Signage | 10000 | Digital Signage
010100.220 | Smart Box | 10000 | Smart Box
010100.230 | Owner Office Trailers | 10000 | Owner Office Trailers
010100.235 | Office Trailer Lot Rental | 10000 | Office Trailer Lot Rental
010100.240 | Office Trailer Lot Improvements | 10000 | Office Trailer Lot Improvements
011030.020 | Precon - Misc Preconstruction Costs | 10000 | Precon - Misc Preconstruction Costs
011100.010 | Temporary Utilities | 11100 | Summary of Work
011100.020 | Temp Electricity - Consumption | 11100 | Summary of Work
011100.030 | Temp Electricity - Install Temp Vault | 11100 | Summary of Work
011100.040 | Temp Power and Light - Install | 11100 | Summary of Work
011100.050 | Temp Heating Fuel (Oil/Gas/Steam) | 11100 | Summary of Work
011100.060 | Temp Cooling | 11100 | Summary of Work
011100.070 | Temp Toilets | 11100 | Summary of Work
011100.080 | Temp Construction Water | 11100 | Summary of Work
011100.090 | Temp Sewer | 11100 | Summary of Work
011100.100 | Temp Utilities - Deposits | 11100 | Summary of Work
011200.070 | Consumables/Meals | 11200 | Multiple Contract Summary
011200.080 | Water/Coffee | 11200 | Multiple Contract Summary
012050.010 | Office Trailer | 11800 | Project Utility Sources
012050.090 | BIM | 11800 | Project Utility Sources
012070.040 | Progress Photos | 11800 | Project Utility Sources
012100.010 | Safety Labor | 12100 | Allowances
012100.020 | Safety Material and Equipment | 12100 | Allowances
012100.030 | Temp Fire Protection | 12100 | Allowances
012100.040 | Temp Railings | 12100 | Allowances
012100.050 | Police Details | 12100 | Allowances
012100.060 | Fire Watch | 12100 | Allowances
012100.065 | Fire Detail | 12100 | Allowances
012100.070 | Security/Watchman Service | 12100 | Allowances
012100.080 | Rail Road Flagmen | 12100 | Allowances
012100.090 | Temp Labor Services | 12100 | Allowances
013100.010 | Rubbish Chute | 13100 | Project Management and Coordination
013100.020 | Interim Cleaning | 13100 | Project Management and Coordination
013100.025 | Field Office Cleaning | 13100 | Project Management and Coordination
013100.030 | Final Cleaning - Building | 13100 | Project Management and Coordination
013100.040 | Final Cleaning - Parking | 13100 | Project Management and Coordination
013100.050 | Glass Cleaning | 13100 | Project Management and Coordination
013100.060 | Dumpsters | 13100 | Project Management and Coordination
013529.000 | Health, Safety, and Emergency Response Procedures | 13500 | Special Procedures
014100.010 | Temp Mobile Cranes - Use | 14100 | Regulatory Requirements
014100.020 | Temporary Tower Cranes - Install/Remove | 14100 | Regulatory Requirements
014100.030 | Temporary Tower Cranes - Use | 14100 | Regulatory Requirements
014100.040 | Temporary Tower Cranes - Power Supply | 14100 | Regulatory Requirements
014100.050 | Temporary Tower Cranes - Construct/Remove Base | 14100 | Regulatory Requirements
014100.060 | Temporary Hoists - Install/Remove | 14100 | Regulatory Requirements
014100.070 | Temporary Hoists - Use | 14100 | Regulatory Requirements
014100.075 | Temporary Hoists - Operator | 14100 | Regulatory Requirements
014100.080 | Temporary Hoists - Loading Platform | 14100 | Regulatory Requirements
014100.090 | Temporary Scaffolding and Platforms | 14100 | Regulatory Requirements
014100.100 | Temporary Swing Staging | 14100 | Regulatory Requirements
014100.110 | Temporary Elevators - Protect Finished Cabs | 14100 | Regulatory Requirements
014100.120 | Temporary Elevators - Operator | 14100 | Regulatory Requirements
014100.130 | Trucking | 14100 | Regulatory Requirements
015100.010 | Temp Access Roads | 15100 | Temporary Utilities
015100.020 | Temp Parking Areas | 15100 | Temporary Utilities
015100.030 | Traffic Control | 15100 | Temporary Utilities
015100.040 | Street / Sidewalk Permits | 15100 | Temporary Utilities
015100.050 | Parking Meter Rental | 15100 | Temporary Utilities
015100.060 | Sidewalk/Parking Lane Deposit | 15100 | Temporary Utilities
015100.070 | Permits | 15100 | Temporary Utilities
016100.010 | Temporary Air Barriers | 16100 | Common Product Requirements
016100.020 | Temporary Dust Barriers | 16100 | Common Product Requirements
016100.030 | Temporary Noise Barriers | 16100 | Common Product Requirements
016100.040 | Temporary Barricades | 16100 | Common Product Requirements
016100.050 | Temporary Fencing | 16100 | Common Product Requirements
016100.060 | Temporary Protective Walkways | 16100 | Common Product Requirements
016100.070 | Temporary Security Barriers | 16100 | Common Product Requirements
016100.080 | Temporary Security Enclosures | 16100 | Common Product Requirements
016100.090 | Temporary Tree and Plant Protection | 16100 | Common Product Requirements
016100.100 | Scrim/Screens | 16100 | Common Product Requirements
016100.110 | Move Fencing | 16100 | Common Product Requirements
017100.010 | Winter Conditions - Fuel | 17100 | Examination and Preparation
017100.020 | Winter Conditions - Heaters | 17100 | Examination and Preparation
017100.030 | Winter Conditions - Enclosures | 17100 | Examination and Preparation
017100.040 | Winter Conditions - Winter Concrete | 17100 | Examination and Preparation
017100.050 | Winter Conditions - Snow Removal | 17100 | Examination and Preparation
017100.060 | Winter Conditions - Other | 17100 | Examination and Preparation
017400.000 | Cleaning and Waste Management | 17400 | Cleaning and Waste Management
017413.000 | Progress Cleaning | 17400 | Cleaning and Waste Management
017416.000 | Site Maintenance | 17400 | Cleaning and Waste Management
017420.000 | Dust Control | 17400 | Cleaning and Waste Management
017423.000 | Final Cleaning | 17400 | Cleaning and Waste Management
017427.000 | Construction Entrance Maintenance | 17400 | Cleaning and Waste Management
018100.010 | Legal | 18100 | Facility Performance Requirements
018100.020 | Structural | 18100 | Facility Performance Requirements
018100.030 | Roofing | 18100 | Facility Performance Requirements
018100.040 | Waterproofing | 18100 | Facility Performance Requirements
018100.050 | Specialty | 18100 | Facility Performance Requirements
018100.060 | Testing and Inspection | 18100 | Facility Performance Requirements
018100.070 | Scheduling | 18100 | Facility Performance Requirements
018100.075 | Pull Planning | 18100 | Facility Performance Requirements
018100.080 | Computer/Technology | 18100 | Facility Performance Requirements
018100.085 | Construction Cameras | 18100 | Facility Performance Requirements
019100.010 | Suffolk Signage | 19100 | Commissioning
019100.020 | Temp Owner Project Signage | 19100 | Commissioning
019100.030 | Core Boards | 19100 | Commissioning
019999.000 | General Requirements Allocation | 19400 | Facility Decommissioning
019999.999 | General Requirements - Fee Contingency | 19400 | Facility Decommissioning
980000.000 | General Conditions | 980000 | General Conditions
980100.190 | Punch List | 980000 | Punch List
981000.000 | Preconstruction | 980000 | Preconstruction
981010.010 | Precon - Director of Precon | 980000 | Precon - Director of Precon
981010.020 | Precon - Chief Estimator | 980000 | Precon - Chief Estimator
981010.030 | Precon - Preconstruction Manager | 980000 | Precon - Preconstruction Manager
981010.040 | Precon - Sr. Estimator | 980000 | Precon - Sr. Estimator
981010.050 | Precon - Estimator | 980000 | Precon - Estimator
981010.060 | Precon - MEP Estimator | 980000 | Precon - MEP Estimator
981010.070 | Precon - Regional Scheduling Director | 980000 | Precon - Regional Scheduling Director
981010.080 | Precon - Scheduling Engineer | 980000 | Precon - Scheduling Engineer
981010.090 | Precon - Engineering Manager | 980000 | Precon - Engineering Manager
981010.100 | Precon - Regional BIM/VDC Director | 980000 | Precon - Regional BIM/VDC Director
981010.110 | Precon - BIM/VDC Manager | 980000 | Precon - BIM/VDC Manager
981010.120 | Precon - Purchasing Manager | 980000 | Precon - Purchasing Manager
981010.130 | Precon - Project Executive | 980000 | Precon - Project Executive
981010.140 | Precon - Senior Project Manager | 980000 | Precon - Senior Project Manager
981010.150 | Precon - Project Manager | 980000 | Precon - Project Manager
981010.160 | Precon - Assistant Project Manager | 980000 | Precon - Assistant Project Manager
981010.170 | Precon - General Superintendent | 980000 | Precon - General Superintendent
981010.180 | Precon - Senior Superintendent | 980000 | Precon - Senior Superintendent
981010.190 | Precon - Superintendent | 980000 | Precon - Superintendent
981030.010 | Precon - Prints and Copies | 980000 | Precon - Prints and Copies
981030.020 | Precon - Misc Preconstruction Costs | 980000 | Precon - Misc Preconstruction Costs
981100.080 | Temp Construction Water | 981100 | Preconstruction Staffing
982010.010 | Director of Field Ops | 981200 | Preconstruction Expenses
982010.020 | VP Operations | 981200 | Preconstruction Expenses
982010.030 | Regional Safety Director | 981200 | Preconstruction Expenses
982010.040 | Regional Scheduling Director | 981200 | Preconstruction Expenses
982010.050 | Scheduling Engineer | 981200 | Preconstruction Expenses
982010.060 | Regional Engineering Director | 981200 | Preconstruction Expenses
982010.070 | Sr. Engineering | 981200 | Preconstruction Expenses
982010.080 | Engineering Manager | 981200 | Preconstruction Expenses
982010.090 | Regional BIM/VDC Director | 981200 | Preconstruction Expenses
982010.100 | BIM/VDC Manager | 981200 | Preconstruction Expenses
982010.110 | BIM/VDC Coordinator | 981200 | Preconstruction Expenses
982010.120 | BIM/VDC Operator | 981200 | Preconstruction Expenses
982010.130 | Director of Precon | 981200 | Preconstruction Expenses
982010.140 | Chief Estimator | 981200 | Preconstruction Expenses
982010.150 | Preconstruction Manager | 981200 | Preconstruction Expenses
982010.160 | Sr. Estimator | 981200 | Preconstruction Expenses
982010.170 | Estimator | 981200 | Preconstruction Expenses
982010.180 | MEP Estimator | 981200 | Preconstruction Expenses
982010.190 | Purchasing Manager | 981200 | Preconstruction Expenses
982010.200 | Project Accountant | 981200 | Preconstruction Expenses
982010.210 | Project Controller | 981200 | Preconstruction Expenses
982010.220 | Compliance | 981200 | Preconstruction Expenses
982010.225 | Compliance Director | 981200 | Preconstruction Expenses
982010.230 | Quality Control Manager | 981200 | Preconstruction Expenses
982010.240 | Project Executive | 981200 | Preconstruction Expenses
982010.250 | Senior Project Manager | 981200 | Preconstruction Expenses
982010.260 | Project Manager | 981200 | Preconstruction Expenses
982010.270 | Assistant Project Manager | 981200 | Preconstruction Expenses
982010.280 | MEP Project Manager | 981200 | Preconstruction Expenses
982010.290 | Project Engineer (Office) | 981200 | Preconstruction Expenses
982010.300 | Administrative Assistant | 981200 | Preconstruction Expenses
982010.310 | General Superintendent | 981200 | Preconstruction Expenses
982010.320 | Senior Superintendent | 981200 | Preconstruction Expenses
982010.330 | Superintendent | 981200 | Preconstruction Expenses
982010.340 | Assistant Superintendent | 981200 | Preconstruction Expenses
982010.350 | Safety Manager | 981200 | Preconstruction Expenses
982010.360 | Project Engineer (Field) | 981200 | Preconstruction Expenses
982010.370 | Insurance Admin | 981200 | Preconstruction Expenses
982010.380 | Intern/Career Start | 981200 | Preconstruction Expenses
982010.900 | Labor Increases | 981200 | Preconstruction Expenses
982030.010 | Weekly Parking Fees | 981200 | Preconstruction Expenses
982030.020 | Recruiting Charges | 981200 | Preconstruction Expenses
982030.025 | Travel | 981200 | Preconstruction Expenses
982030.030 | Mileage | 981200 | Preconstruction Expenses
982030.040 | Airfare | 981200 | Preconstruction Expenses
982030.050 | Hotel | 981200 | Preconstruction Expenses
982030.060 | Car Rental | 981200 | Preconstruction Expenses
982030.070 | House/Apartment Rental | 981200 | Preconstruction Expenses
982030.080 | Tolls | 981200 | Preconstruction Expenses
982030.090 | Food Allowance | 981200 | Preconstruction Expenses
982030.100 | Vehicle Fuel | 981200 | Preconstruction Expenses
982050.010 | Office Trailer | 981200 | Preconstruction Expenses
982050.020 | Office Furniture and Equipment | 981200 | Preconstruction Expenses
982050.025 | Office Other | 981200 | Preconstruction Expenses
982050.030 | Communications | 981200 | Preconstruction Expenses
982050.040 | Computer Equipment | 981200 | Preconstruction Expenses
982050.045 | Procore | 981200 | Preconstruction Expenses
982050.050 | On Trac | 981200 | Preconstruction Expenses
982050.060 | DBO2 | 981200 | Preconstruction Expenses
982050.070 | Vela | 981200 | Preconstruction Expenses
982050.080 | Misc. Software | 981200 | Preconstruction Expenses
982050.085 | LGB Tracker | 981200 | Preconstruction Expenses
982050.090 | BIM | 981200 | Preconstruction Expenses
982050.095 | Radios | 981200 | Preconstruction Expenses
982050.100 | Cell Phones | 981200 | Preconstruction Expenses
982050.110 | Field Internet Communications | 981200 | Preconstruction Expenses
982070.010 | Suffolk Signage | 981200 | Preconstruction Expenses
982070.020 | Postage and Courier | 981200 | Preconstruction Expenses
982070.030 | Marketing Photographs | 981200 | Preconstruction Expenses
982070.040 | Progress Photos | 981200 | Preconstruction Expenses
982070.050 | Office Supplies | 981200 | Preconstruction Expenses
982070.060 | Permits | 981200 | Preconstruction Expenses
982070.070 | Prints and Copies | 981200 | Preconstruction Expenses
982080.010 | Owner Office Trailer | 981200 | Preconstruction Expenses
982080.020 | Owner Office Furniture and Equip. | 981200 | Preconstruction Expenses
982080.030 | Owner IT and Support Charges | 981200 | Preconstruction Expenses
982080.040 | Security/Watchman Service | 981200 | Preconstruction Expenses
983010.000 | Storage Trailer | 982500 | Owner Support
983020.000 | Tools and Equipment | 982500 | Owner Support
983030.000 | Safety Material and Equipment | 982500 | Owner Support
983050.010 | Safety Allocation | 982500 | Owner Support
983050.020 | Lean Allocation | 982500 | Owner Support
984100.010 | Temp Toilets | 982500 | Owner Support
984100.020 | Dumpsters | 982500 | Owner Support
989000.000 | Warranty | 982500 | Owner Support
989999.000 | General Conditions Allocation | 982500 | Owner Support
989999.999 | General Conditions - Fee Contingency | 982500 | Owner Support

## splash (hidden)
dataSMART GCs & GRs
MACROS MUST BE ENABLED TO USE THIS WORKBOOK
Close this workbook and reopen. When this workbook opens, select 'ENABLE' when prompted.
If you do not see a prompt to enable Macros, follow the below steps:
[1] Click the 'File' tab in the menu header above
[2] Select 'Options' in the navigation bar on the left
[3] Select 'Trust Center' in the left navigation bar
[4] Click the 'Trust Center Settings' button on the middle right
[5] Under the Macro Settings header, click 'Disable all macros with notification'
[6] Close this workbook and excel, select 'ENABLE' when prompted
Click Anywhere For Startup