## Settings
Project |  |  | PreCon Start |  | Contruction Start |  |  | PTO Reimbursable | 2080
Location |  |  | PreCon Finish |  | Construction Finish |  |  | 4wks PTO Non-Reimbursable | 1760
Region | Boston |  | Duration | #NAME? | Duration | #NAME? |  | 3wks PTO Non-Reimbursable | 1840
Sector | Residential |  |  | #NAME? |  | #NAME? |  | SELECT | 2080
Ops Job # |  |  | Estimating LIT | 62% | Units |  | ea
Precon Task # |  |  | Construction LIT | 62% | Area |  | gsf
Date | 2018-08-15 08:16 |  | Precon Raises | 4%
|  |  | Construction Raises | 4% | Totals
Project Cost |  |  |  |  | Preconstruction | 0
|  |  | IT/week | 92 | Construction | 0
|  |  | Iphone/week | 58 | General Conditions | #NAME?
Vacation | PTO Reimbursable |  | Gas/week | 115 | General Requirements | #NAME?
| SECTORS | REGIONS
| Mixed-Use | Boston
| Parking | New York
| Office | Miami
| Retail | West Palm Beach
| Hospitality & Entertainment | Estero
| Residential | Tampa
| Elder Care | Dallas
| Health Care | San Diego
| Laboratory | Los Angeles
| Education | San Francisco
Community / Cultural
Sports / Recreation
Food Service
Manufacturing / Warehouse
Site / Infrastructure
Energy / Communications
Transportation
Government

## meta (hidden)
1 | 1 | 1

## Staff Detail (hidden)
[30 empty] | 0 | 0
2018-08-15 08:16
| PreCon Start |  | Duration | #NAME? | IT/wk | 92 |  | Estimating LIT | 62%
| PreCon Finish | 0 |  | #NAME? | Iphone/wk | 58 |  | Construction LIT | 62%
| Contruction Start | 0 | Duration | #NAME? | Gas/wk | 115 |  | Precon Raises | 4%
| Construction Finish |  |  | #NAME? |  |  |  | Construction Raises | 4%
1
|  |  |  | Annual Car Allow | Start Month |  | Start Date | Finish Date |  |  |  | 0 |  | Grand Total | Man Weeks | Sort Order | # of weeks | IT /week | IPhone /week | Gas /week | IT total | Iphone total | Gas total | Labor total | Total Annual | [6 empty] | #NUM! | 1900-01-30
| Job Title | Name | Salary |  |  | Duration |  |  | % |  | -2 | 1 | Rate | [13 empty] | Grand Total | staff ct | 0 |  |  | -1 | 2
| Precon | [6 empty] | graph staffing | [19 empty] | prelabor | 0
[8 empty] | Subtotals: |  |  | 0% |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
| Construction | [8 empty] | 0 | 0 | [16 empty] | conlabor | 0
[8 empty] | Subtotals: |  |  | 0% |  |  | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0
[5 empty] | #NAME? | #NAME? | 0 | 0 |  |  |  |  | #NAME? | #NAME? | 0 |  | 0 | 92 | 58 | 115 | 0 | 0 | 0 | #NAME? | #NAME? |  | #NAME?
[5 empty] | 1 | #NAME? | 0 | 0 |  |  |  |  | #NAME? | #NAME? | 0 |  | 0 | 92 | 58 | 115 | 0 | 0 | 0 | #NAME? | #NAME? |  | #NAME?
[13 empty] | #NAME? | #NAME? | 0 |  | 0 | 92 | 58 | 115 | 0 | 0 | 0 | #NAME? | #NAME? |  | #NAME?
[5 empty] | #NAME? | #NAME? | 0 | 0 |  |  |  |  | #NAME? | #NAME? | 0 |  | 0 | 92 | 58 | 115 | 0 | 0 | 0 | #NAME? | #NAME? |  | #NAME?
dp | New Phase: | [5 empty] | Start? | Finish? |  | 0 | 0
[8 empty] | Subtotals: | [5 empty] | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase Start |  | 0
Phase Finish

## Labor Gantt (hidden)
|  | Start Week | Duration | Pred | Lag | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 1
Add Phase Here:
|  | Start Week | Duration | % Work
| Construction | 1 | 0 | 0%
dp
labor gantt

## Non-Staff Labor (hidden)
|  | Clean-Up Labor |  |  | Safety (C & L) |  |  | Police |  |  | Labor Steward |  |  | Carpenter Steward |  |  | Fire Watch |  |  | Template
Index | Week | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | OT | Total | Crew Size | Rate | OT | Total
Subtotals |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Foreman |  |  |  | 0 |  |  | 0
TOTALS |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
1 | 1900-01-06 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Formulas:
Week = IFERROR(OFFSET([Week],-1,0)+7,Settings!\cstart)
non-staff labor

## Rate Tables (hidden)
Clean-Up Labor |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 103.02 | 130.8354 | 97.75 | 124.1425 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0
2018-12-01 | 101 | 128.27 | 99.25 | 126.0475 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0 | 99.25 | 0
2018-06-01 | 99.25 | 126.0475 | 101 | 128.27 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0 | 101 | 0
2017-12-01 | 97.75 | 124.1425 | 103.02 | 130.8354 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0 | 103.02 | 0
Laborer Foreman |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 109.14 | 138.6078 | 103.75 | 131.7625 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0
2018-12-01 | 107 | 135.89 | 105.5 | 133.985 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0 | 105.5 | 0
2018-06-01 | 105.5 | 133.985 | 107 | 135.89 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0 | 107 | 0
2017-12-01 | 103.75 | 131.7625 | 109.14 | 138.6078 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0 | 109.14 | 0
Safety & Carpentry |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 125.46 | 159.3342 | 118 | 149.86 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0
2018-09-01 | 123 | 156.21 | 120.5 | 153.035 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0 | 120.5 | 0
2018-03-01 | 120.5 | 153.035 | 123 | 156.21 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0 | 123 | 0
2017-09-01 | 118 | 149.86 | 125.46 | 159.3342 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0 | 125.46 | 0
Carpenter Foreman |  |  | Boston | 1.27 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 134.895 | 171.3167 | 127.5 | 161.925 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0
2018-09-01 | 132.25 | 167.9575 | 130 | 165.1 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0 | 130 | 0
2018-03-01 | 130 | 165.1 | 132.25 | 167.9575 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0 | 132.25 | 0
2017-09-01 | 127.5 | 161.925 | 134.895 | 171.3167 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0 | 134.895 | 0
Police |  |  | Boston |  | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
0 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66 | 45 | 66
Labor Steward |  |  | Boston | 1.25 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-06-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-12-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-06-01 | 1 | 1.25 | 1 | 1.25 | 1.1 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0
2017-12-01 | 1 | 1.25 | 1 | 1.25 | 1.17 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0
Carpenter Steward |  |  | Boston | 1.25 | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
2019-03-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-09-01 | 1 | 1.25 | 1 | 1.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
2018-03-01 | 1 | 1.25 | 1 | 1.25 | 1.1 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0 | 1.25 | 0
2017-09-01 | 1 | 1.25 | 1 | 1.25 | 1.17 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0 | 1.5 | 0
Fire Watch |  |  | Boston |  | New York |  | Miami |  | West Palm Beach |  | Estero |  | Tampa |  | Dallas |  | San Diego |  | Los Angeles |  | San Francisco
0 | 45 | 66 | 45 | 66 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0

## GCs Detail (hidden)
[8 empty] | regions | sectors | cost code
#NAME?
| Region: | Boston | weeks : | #NAME? | units : | 0
| Sector: | Residential | months : | #NAME? | area : | 0
| PROJECT STAFFING EXPENSES |  |  |  |  | #NAME? | [
| Weekly Parking Fees |  | #NAME? | wks | 300 | #NAME? | 1 |  |  | 98 22 00
| Recruiting Charges |  | 0 | lsum | 0 | 0 | 1 |  |  | 98 22 00
| Mileage |  | 0 | miles | 0.55 | 0 | 1 |  |  | 98 22 00
| Airfare |  | 0 | flights | 0 | 0 | 1 |  |  | 98 22 00
| TBD |  | 0 | nights | 0 | 0 | 1 |  |  | 98 22 00
| Car Rental |  | 0 | days | 400 | 0 | 1 |  |  | 98 22 00
| House/Apartment Rental |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 98 22 00
| Moving/Relocation |  | #NAME? | wks | 0 | #NAME? | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 22 00
| Tolls |  | #NAME? | wks | 0 | #NAME? | 1 |  |  | 98 22 00
| Food Allowance |  | #NAME? | wks | 0 | #NAME? | 1 |  |  | 98 22 00
]
| PROJECT TRAILERS |  |  |  |  | 0 | [
1
]
| TEMPORARY OFFICE RENTAL |  |  |  |  | #NAME? | [
| Rental Fees |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 98 23 00
| Build-Out Of Office Space |  | 1 | lsum | 0 | 0 | 1 |  |  | 98 23 00
| Utilities |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 98 23 00
| Demolition & Restore to Original Condition |  | 1 | lsum | 0 | 0 | 1 |  |  | 98 23 00
]
| SUFFOLK OFFICE FUNITURE & EQUIPMENT |  |  |  |  | #NAME? | [
| Digital Camera |  | 0 | ea | 500 | 0 | 1 |  |  | 98 23 00
| Jobsite Live Streaming Camera - Earthcam |  | 0 | set-up | 12000 | 0 | 1 |  |  | 98 23 00
| Jobsite Live Streaming Camera - Earthcam ($600/mth fee plus $300/mth for internet fee) |  | #NAME? | mos | 900 | #NAME? | 1 |  |  | 98 23 00
| Cell Phone Charging Stations |  | 0 | ea | 1250 | 0 | 1 |  |  | 98 23 00
| Copiers |  | 0 | ea | #NAME? | #NAME? | 1 |  |  | 98 23 00
| Copier Maintenance |  | #NAME? | mos | 500 | #NAME? | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 23 00
| Office Supplies |  | #NAME? | mos | 350 | #NAME? | 1 |  |  | 98 23 00
| Office Furniture for each staff member (Desks, Chairs, File Cabinet) |  | 0 | ea | 600 | 0 | 1 |  |  | 98 23 00
| Office Furniture (Conf. Tables, Chairs, Plan Tables, Filing Cabinets) |  | 0 | ls | 600 | 0 | 1 |  |  | 98 23 00
| Consumables |  | #NAME? | mos | 200 | #NAME? | 1 |  |  | 98 23 00
| Team Lunch (Owner Meetings) |  | #NAME? | mos | 500 | #NAME? | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 23 00
| Bottled Water/Coffee |  | #NAME? | mos | 250 | #NAME? | 1 |  |  | 98 23 00
]
| INFORMATION TECHNOLOGY & SUPPORT |  |  |  |  | #NAME? | [
| Internet set-up / job site set up |  | 0 | lines | 1000 | 0 | 1 |  |  | 98 23 00
| Internet Monthly Cost |  | #NAME? | mos | #NAME? |  | 1 |  |  | 98 23 00
| Mifi Set-up Cost (Cradlepoints) |  | 0 | ea | 300 | 0 | 1 |  |  | 98 23 00
| Mifi Monthly Cost |  | #NAME? | mos | 265 | #NAME? | 1 |  |  | 98 23 00
| Cisco PoE Switch (One required for every job) - Good for Up to 20 Users |  | 0 | ea | 4600 | 0 | 1 |  |  | 98 23 00
| Internal Wireless Access Point (Trailer) |  | 0 | ea | 600 | 0 | 0 | Tampa Dallas San Diego |  | 98 23 00
| External Wireless Access Point (Site) |  | 0 | ea | 1820 | 0 | 1 | Boston San Diego Los Angeles San Francisco |  | 98 23 00
| Cisco VoiP phone |  | 0 | ea | 750 | 0 | 1 |  |  | 98 23 00
| Cisco Conference Star phone |  | 0 | ea | 1200 | 0 | 1 |  |  | 98 23 00
| Red Analog Emergency Phone |  | 0 | ea | 50 | 0 | 1 |  |  | 98 23 00
| File Server, Rack, UPS, SkySync License |  | 0 | ea | 25000 | 0 | 1 |  |  | 98 23 00
]
| COMPUTER EQUIPMENT |  |  |  |  | 0 | [
| Printer |  | 0 | ea | 450 | 0 | 1 |  |  | 98 23 00
| Desktop Computer |  | 0 | ea | 2265 | 0 | 1 |  |  | 98 23 00
| Laptop Standard |  | 0 | ea | 1500 | 0 | 1 |  |  | 98 23 00
| Laptop BIM High Spec |  | 0 | ea | 4500 | 0 | 1 |  |  | 98 23 00
| 24" Monitor |  | 0 | ea | 150 | 0 | 1 |  |  | 98 23 00
| 27" Monitor |  | 0 | ea | 150 | 0 | 1 |  |  | 98 23 00
| 27" DELL 4K monitor |  | 0 | ea | 450 | 0 | 1 |  |  | 98 23 00
| Digital Signage |  | 0 | ea | 2500 | 0 | 1 |  |  | 98 23 00
| Microsoft Surface Hub |  | 0 | ea | 1500 | 0 | 1 |  |  | 98 23 00
| Apple TV (iPad Screen Mirroring) |  | 0 | ea | 70 | 0 | 1 |  |  | 98 23 00
| Field iPad |  | 0 | ea | 860 | 0 | 1 |  |  | 98 23 00
]
| PROCORE |  |  |  |  | 0 | [
| Procore Fee |  | 0 | contract | 0.07% | 0 | 1 |  |  | 98 23 00
]
| SUFFOLK SAFETY APPLICATION |  |  |  |  | #NAME? | [
| Safety Application - per each on site staff |  | #NAME? | mos | 65 | #NAME? | 1 |  |  | 98 23 00
]
| BIM 360 |  |  |  |  | 0 | [
| BIM 360 |  | 0 | contract | 0.025% | 0 | 1 |  |  | 98 23 00
]
| BIM |  |  |  |  | 0 | [
| Scanning an Existing Building |  | 0 | sf | 0.3 | 0 | 1 |  |  | 98 23 00
| QA/QC of a New Building |  | 0 | sf | 0.6 | 0 | 1 |  |  | 98 23 00
]
| LEAN CONSULTING |  |  |  |  | #NAME? | [
| Internal Consulting |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 98 24 00
| Touchplan Fees, Monthly |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 98 24 00
| Touchplan Fees, One Time Fee |  | 1 | lsum | #NAME? | #NAME? | 1 |  |  | 98 24 00
]
| MISCELLANEOUS EXPENSES |  |  |  |  | 5000 | [
| Suffolk Project Sign |  | 1 | lsum | 3000 | 3000 | 1 |  |  | 98 24 00
| Marketing Photographs |  | 1 | lsum | 2000 | 2000 | 1 |  |  | 98 24 00
| Aerial Photos |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 98 24 00
| Client Entertainment |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 24 00
| Association Dues - TEXO |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 98 24 00
| Groundbreaking Ceremony |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 24 00
| Topping Off Ceremony |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 98 24 00
| Team-Building Event |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 98 24 00
]
0
| Trailer | [8 empty] | 982300
| Rent |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 982300
| Delivery |  | 1 | lsum | #NAME? | #NAME? | 1 |  |  | 982300
| Pick-up |  | 1 | lsum | #NAME? | #NAME? | 1 |  |  | 982300
| Aluminum Steps |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 982300
| Security System |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 982300
| Utility Connections |  | 1 | lsum | #NAME? | #NAME? | 1 |  |  | 982300
| Utility Consumption |  | #NAME? | mos | #NAME? | #NAME? | 1 |  |  | 982300
| Skirting |  | 1 | lsum | #NAME? | #NAME? | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 982300
remove carry
prorate
catch all
Note on E60: Includes Microsoft Licensing
Note on E61: Includes Microsoft Licensing, keyboard, bag and docking station
Note on E62: Includes Microsoft Licensing, keyboard, bag and docking station

## GRs Detail (hidden)
[8 empty] | regions | sectors | cost code
#NAME?
| Region: | Boston | weeks : | #NAME? | units : | 0
| Sector: | Residential | months : | #NAME? | area : | 0
| REPROGRAPHICS |  |  |  |  | 0 | [
| Pre-Construction |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Construction |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
]
| POSTAGE & COURIER |  |  |  |  | 0 | [
| Pre-Construction |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Construction |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
]
| EXPLORITORY & SURVEYING SERVICES |  |  |  |  | 0 | [
| Exploratory Investigations |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Surveying Equipment |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Surveying Services |  | 0 | day | 1600 | 0 | 1 |  |  | 01 10 00
| Survey Exist. Cond. / As-Builts |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
]
| CONSTRUCTION PARKING & TRANSPORTATION |  |  |  |  | 0 | [
| Rental of Offsite Parking Lot |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Parking Shuttle Van |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Parking Shuttle Van Driver |  | 0 | day | 280 | 0 | 1 |  |  | 01 10 00
]
| CONSULTING SERVICES |  |  |  |  | 0 | [
| Misc. Consulting Services |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Envelope Consulting Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Structural Consulting Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Equipment Consulting Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Minority / HUB Consulting Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| LEED / Dallas Green Consulting Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Legal Services |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 10 00
| Smoke Control |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 10 00
| Small Business/Work Force Compliance Consultant |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 10 00
| Lean Consulting Services |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Partnering Session |  | 1 | lsum | 0 | 0 | 0 |  | Elder Care Laboratory Education Sports / Recreation | 01 10 00
]
| MISCELLANEOUS SUPPORT & EQUIPMENT |  |  |  |  | #NAME? | [
| Mock Ups (include removal) |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| SkyTrak |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Forklift |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Scissor Lift |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 10 00
| Teamster |  | 0 | wks | 5000 | 0 | 1 | Boston New York San Diego Los Angeles San Francisco |  | 01 10 00
| Trucking/Transportation |  | 1 | lsum | 0 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 01 10 00
| Storage Trailer |  | #NAME? | mos | 165 | #NAME? | 1 |  |  | 01 10 00
| Master Mechanic |  | 0 | wks | 6000 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 01 10 00
| Tools & Equipment |  | #NAME? | mos | 1000 | #NAME? | 1 |  |  | 01 10 00
| Radios |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 10 00
| Rodent Control |  | 0 | mos | 300 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 10 00
| Mock Ups (include removal) |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Off Hours Work Permit |  | 0 | days | 100 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 10 00
| Punch List |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 10 00
| Cut & Patch |  | 1 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 10 00
]
| WATER CONSUMPTION |  |  |  |  | #NAME? | [
| Water Consumption |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 11 00
]
| ELECTRICITY CONSUMPTION |  |  |  |  | 0 | [
| Electric Consumption |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 11 00
| Temp. Electric Vault & Service |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 11 00
]
| TEMPORARY TOILETS |  |  |  |  | 0 | [
| Portables |  | 0 | ea | 0 | 0 | 1 |  |  | 01 11 00
| Portable Unit Delivery Fee |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 11 00
| Temp Bathroom Install |  | 0 | ea | 100 | 0 | 1 |  |  | 01 11 00
| Temp Bathroom Remove |  | 0 | ea | 100 | 0 | 1 |  |  | 01 11 00
| Temp Bathroom Cleaning |  | #NAME? | wks | 0 | #NAME? | 1 |  |  | 01 11 00
| Hand Sanitizer |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 01 11 00
| Hand Wash Stations |  | 0 | ea | 0 | 0 | 0 | Dallas |  | 01 11 00
| Gel Pak |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 11 00
| Holding Tanks |  | 0 | ea | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 01 11 00
]
| CONSTRUCTION MANAGEMENT PLAN |  |  |  |  | #NAME? | [
| Sidewalk Bridge |  | 0 | lf | 175 | 0 | 1 |  |  | 01 21 00
| New Traffic Markings |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 21 00
| Remove Old/Existing Traffic Markings |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 21 00
| Temporary Road Signs |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 21 00
| Sidewalk Rental |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
| Street Rental |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
| Covered Pedestrian Walkways |  | #NAME? | mos | 0 | #NAME? | 0 | Dallas |  | 01 21 00
| Car Washes |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| Turnstiles |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| Guard Shack/s |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| Security |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
| Site Security System |  | #NAME? | mos | 0 | #NAME? | 0 | Dallas |  | 01 21 00
| Progress Photos |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| Aerial Photos |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| MultiVista |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 21 00
| Railway Spotter |  | #NAME? | mos | 0 | #NAME? | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Car/Boat Detailing |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Clean Adjacent Building |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 01 21 00
| MOT Plan |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Miscellaneous Permits |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Overtime Inspection Costs |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Access Point Turnstiles |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Hurricane Preparation |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 21 00
| Parking Meter Fees |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
| Off Hours Permit |  | 0 | events | 100 | 0 | 1 |  |  | 01 21 00
]
| CONSTRUCTION FENCE |  |  |  |  | #NAME? | [
| Jersey Barriers |  | 0 | lf/month | 12 | 0 | 1 |  |  | 01 61 00
| Fence on top of Jersey Barriers |  | 0 | lf | 10 | 0 | 1 |  |  | 01 61 00
| Chain Link Fence |  | 0 | lf | 18 | 0 | 1 |  |  | 01 61 00
| Windscreen/Scrim/Red Ribbon |  | 0 | lf | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa Dallas |  | 01 61 00
| Water Barriers |  | 0 | lf | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 61 00
| Gates |  | 0 | ea | 500 | 0 | 1 |  |  | 01 61 00
| Maintenance & Relocations |  | #NAME? | wks | 0 | #NAME? | 1 |  |  | 01 61 00
| Fence Removal |  | 0 | lf | 0 | 0 | 1 |  |  | 01 61 00
| Laborer to Open & Close Gates |  | 0 | hrs | 0 | 0 | 1 |  |  | 01 61 00
]
| SAFETY SUPPLIES & EQUIPMENT |  |  |  |  | #NAME? | [
| Temporary Fire Extinguishers & Stands |  | 0 | ea | 200 | 0 | 1 |  |  | 01 21 00
| Temporary Signage |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 21 00
| First Aid Supplies |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
| Shanty Protection - smoke detector & fire extinguisher |  | 0 | ea | 200 | 0 | 1 | Boston New York San Diego Los Angeles San Francisco |  | 01 21 00
| Shanty Protection - NYC Sprinkler Kit (not required yet - over 40 stories only) |  | 0 | ea | 750 | 0 | 1 | Boston New York San Diego Los Angeles San Francisco |  | 01 21 00
| Fire Department Post (signage, gang box, keys, plans, etc. - over 40 stories only) |  | 0 | ea | 5000 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 01 21 00
| Creation of Temp. Fire Protection Plan (over 40 stories only) |  | 0 | ea | 25000 | 0 | 1 | Boston New York Dallas San Diego Los Angeles San Francisco |  | 01 21 00
| Misc. Safety Supplies (hard hats, safety glasses, harnesses, etc) |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 21 00
]
| MISC LABOR & CLEANING |  |  |  |  | 2000 | [
| Materials |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 74 00
| Cleaning Supplies |  | #NAME? | mos | 0 | #NAME? | 1 |  |  | 01 74 00
| Cleaning Site |  | 0 | hrs | 0 | 0 | 1 |  |  | 01 74 00
| Cleaning Trailers/Office |  | 0 | hrs | 0 | 0 | 1 |  |  | 01 74 00
| Rubbish Chute |  | 0 | floors | 2000 | 0 | 1 |  |  | 01 74 00
| Waste Management Plan |  | 1 | lsum | 2000 | 2000 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 74 00
| Final Cleaning - Building |  | 0 | sf | 0 | 0 | 1 |  |  | 01 74 00
| Final Cleaning - Parking |  | 0 | sf | 0 | 0 | 1 |  |  | 01 74 00
| Final Clean - Exterior Windows |  | 0 | sf | 0 | 0 | 0 | Dallas |  | 017400
| Pre-Clean - Exterior Windows |  | 0 | sf | 0 | 0 | 0 | Dallas |  | 017400
| Final Clean - Interiors |  | 0 | sf | 0 | 0 | 0 | Dallas |  | 017400
| Pre-Clean - Interiors |  | 0 | sf | 0 | 0 | 0 | Dallas |  | 017400
]
| TEMPORARY SAFETY & PROTECTION |  |  |  |  | 0 | [
| Materials |  | 0 | lsum | 0 | 0 | 1 |  |  | 01 21 00
| Temporary Stairs |  | 0 | ea | 0 | 0 | 1 |  |  | 01 21 00
| Perimeter Fall Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
| Elevator Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
| Floor Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
| Door Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
| Window Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
| Temporary Wall Protection |  | 0 | lsum |  | 0 | 1 |  |  | 01 21 00
]
| DUMPSTERS |  |  |  |  | 0 | [
| Dumpsters |  | 0 | loads | 650 | 0 | 1 |  |  | 01 74 00
| Recycle Dumpster Premium |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 74 00
| Post-Sort Services |  | 1 | lsum | 0 | 0 | 0 | Dallas |  | 01 74 00
| Overweight Pulls (10% of total # of loads) |  | 0 | loads | 100 | 0 | 1 |  |  | 01 74 00
]
| PERSONNEL & MATERIAL HOISTING |  |  |  |  | #NAME? | [
| Mobilize, Erect & Dismantle |  | 0 | lsum | 0 | 0 | 1 |  |  | 01 41 00
| Police Details, Cranes, Permits during E & D |  | 0 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Operating Engineers during E & D |  | 0 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Hoist Rental (Single Car) |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Hoist Rental (Double Car) |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Gate Rental |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Gate Installation |  | 0 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 41 00
| Hoist Rental Insurance |  | 0 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Communication Boxes |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Jumps |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Sales Tax |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Operator Car #1 (Regular Time) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Operator Car #2 (Regular Time) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Operator Car #1 (Overtime) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Operator Car #2 (Overtime) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Temporary Interior Elevator Operator (Regular Time) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Temporary Interior Elevator Operator (Overtime) |  | #NAME? | wks | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Overtime Equipment Hours |  | 0 | hrs | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 41 00
| Elevator Maintenance |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Elevator Repairs |  | 1 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Drop Tests |  | 1 | lsum | 0 | 0 | 0 | Miami West Palm Beach Estero Tampa |  | 01 41 00
| Fence Enclosures |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Concrete Pad |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Reinforce Existing Structure @ Tie-Ins |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Loading Docks/Ramps/Overhead Prot. |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Cab Protection |  | 1 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Plywood Partitions @ Gates |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Temporary Power Consumption |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Temporary Power Service |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Threshold Rentals |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| Assist Crane |  | #NAME? | mos | 0 | #NAME? | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
| 3rd Party Certification |  | 1 | lsum | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 41 00
]
| WINTER CONDITIONS / TEMPORARY HEAT |  |  |  |  | 0 | [
| Temporary Heating |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 71 00
| Temporary Cooling |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 71 00
| Temporary De-Humidification |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 71 00
| Negative Air Machines |  | 0 | ea | 0 | 0 | 0 | Dallas |  | 01 71 00
| Dewatering |  | 1 | lsum | 0 | 0 | 1 |  |  | 01 71 00
| Snow Removal from Building |  | 1 | lsum | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Snow Removal from Site |  | 1 | lsum | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Temporary Construction |  | 1 | lsum | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Miscellaneous Heat & Tarps |  | 0 | mos | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Portable Heaters |  | 0 | mos | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Babfar Rental/Install |  | 0 | mos | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Temp. Ductwork |  | 1 | lsum | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Use/cln perm.system |  | 0 | mos | 0 | 0 | 1 | Boston New York |  | 01 71 00
| Fuel |  | 0 | wks | 0 | 0 | 1 | Boston New York |  | 01 71 00
]
| STAGING & SCAFFOLDING |  |  |  |  | 0 | [
| Exterior Scaffolding first months rental & dismantle |  | 0 | ea | 0 | 0 | 1 |  |  | 01 41 00
| Exterior Scaffolding monthly rental |  | 0 | mos | 0 | 0 | 1 |  |  | 01 41 00
| Exterior Scaffolding move planks |  | 0 | days | 0 | 0 | 1 |  |  | 01 41 00
| Interior Scaffolding first months rental & dismantle |  | 0 | ea | 0 | 0 | 1 |  |  | 01 41 00
| Interior Scaffolding monthly rental |  | 0 | mos | 0 | 0 | 1 |  |  | 01 41 00
| Interior Scaffolding move planks |  | 0 | days | 0 | 0 | 1 |  |  | 01 41 00
]
| TESTING & INSPECTIONS |  |  |  |  | 0 | [
| Soils |  | 0 | ea | 0 | 0 | 1 |  |  | 01 81 00
| Concrete |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 81 00
| Steel |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 81 00
| Spray Fireproofing |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 81 00
| Curtainwall & Windows |  | 0 | ea | 0 | 0 | 1 | Boston New York Miami West Palm Beach Estero Tampa San Diego Los Angeles San Francisco |  | 01 81 00
]
| LABOR ITEMS |  |  |  |  | 0 | [
| Clean-Up Labor |  | 1 | lsum | 0 | 0 | 1
| Safety (C & L) |  | 1 | lsum | 0 | 0 | 1
| Police |  | 1 | lsum | 0 | 0 | 1
| Labor Steward |  | 1 | lsum | 0 | 0 | 1
| Carpenter Steward |  | 1 | lsum | 0 | 0 | 1
| Fire Watch |  | 1 | lsum | 0 | 0 | 1
]
0
|  |  | 1 | lsum |  | 0 | 1
remove carry
prorate
catch all
Note on E46: Includes Microsoft Licensing
Note on E47: Includes Microsoft Licensing, keyboard, bag and docking station
Note on E48: Includes Microsoft Licensing, keyboard, bag and docking station

## GCs Owner (hidden)
0
General Conditions
2018-08-15 08:16
|  | Project Staffing: |  | % of Time | Bill Rate | QT | Unit | Total
|  | Precon | 0 | 0% | 0 | 0 | wks | 0
|  | Construction | 0 | 0% | 0 | 0 | wks | 0
0
|  | SUBTOTAL | [5 empty] | 0
|  | PROJECT STAFFING EXPENSES |  |  | 0% | 0 | 0 | 0
|  | Weekly Parking Fees |  |  | 300 | #NAME? | wks | #NAME?
|  | Recruiting Charges |  |  | 0 | 0 | lsum | 0
|  | Mileage |  |  | 0.55 | 0 | miles | 0
|  | Airfare |  |  | 0 | 0 | flights | 0
|  | TBD |  |  | 0 | 0 | nights | 0
|  | Car Rental |  |  | 400 | 0 | days | 0
|  | House/Apartment Rental |  |  | 0 | #NAME? | mos | #NAME?
|  | Moving/Relocation |  |  | 0 | #NAME? | wks | #NAME?
|  | Tolls |  |  | 0 | #NAME? | wks | #NAME?
|  | Food Allowance |  |  | 0 | #NAME? | wks | #NAME?
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | PROJECT TRAILERS |  |  | 0% | 0 | 0 | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | TEMPORARY OFFICE RENTAL |  |  | 0% | 0 | 0 | 0
|  | Rental Fees |  |  | 0 | #NAME? | mos | #NAME?
|  | Build-Out Of Office Space |  |  | 0 | 1 | lsum | 0
|  | Utilities |  |  | 0 | #NAME? | mos | #NAME?
|  | Demolition & Restore to Original Condition |  |  | 0 | 1 | lsum | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | SUFFOLK OFFICE FUNITURE & EQUIPMENT |  |  | 0% | 0 | 0 | 0
|  | Digital Camera |  |  | 500 | 0 | ea | 0
|  | Jobsite Live Streaming Camera - Earthcam |  |  | 12000 | 0 | set-up | 0
|  | Jobsite Live Streaming Camera - Earthcam ($600/mth fee plus $300/mth for internet fee) |  |  | 900 | #NAME? | mos | #NAME?
|  | Cell Phone Charging Stations |  |  | 1250 | 0 | ea | 0
|  | Copiers |  |  | #NAME? | 0 | ea | #NAME?
|  | Copier Maintenance |  |  | 500 | #NAME? | mos | #NAME?
|  | Office Supplies |  |  | 350 | #NAME? | mos | #NAME?
|  | Office Furniture for each staff member (Desks, Chairs, File Cabinet) |  |  | 600 | 0 | ea | 0
|  | Office Furniture (Conf. Tables, Chairs, Plan Tables, Filing Cabinets) |  |  | 600 | 0 | ls | 0
|  | Consumables |  |  | 200 | #NAME? | mos | #NAME?
|  | Team Lunch (Owner Meetings) |  |  | 500 | #NAME? | mos | #NAME?
|  | Bottled Water/Coffee |  |  | 250 | #NAME? | mos | #NAME?
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | INFORMATION TECHNOLOGY & SUPPORT |  |  | 0% | 0 | 0 | 0
|  | Internet set-up / job site set up |  |  | 1000 | 0 | lines | 0
|  | Internet Monthly Cost |  |  | #NAME? | #NAME? | mos | #NAME?
|  | Mifi Set-up Cost (Cradlepoints) |  |  | 300 | 0 | ea | 0
|  | Mifi Monthly Cost |  |  | 265 | #NAME? | mos | #NAME?
|  | Cisco PoE Switch (One required for every job) - Good for Up to 20 Users |  |  | 4600 | 0 | ea | 0
|  | Internal Wireless Access Point (Trailer) |  |  | 600 | 0 | ea | 0
|  | External Wireless Access Point (Site) |  |  | 1820 | 0 | ea | 0
|  | Cisco VoiP phone |  |  | 750 | 0 | ea | 0
|  | Cisco Conference Star phone |  |  | 1200 | 0 | ea | 0
|  | Red Analog Emergency Phone |  |  | 50 | 0 | ea | 0
|  | File Server, Rack, UPS, SkySync License |  |  | 25000 | 0 | ea | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | COMPUTER EQUIPMENT |  |  | 0% | 0 | 0 | 0
|  | Printer |  |  | 450 | 0 | ea | 0
|  | Desktop Computer |  |  | 2265 | 0 | ea | 0
|  | Laptop Standard |  |  | 1500 | 0 | ea | 0
|  | Laptop BIM High Spec |  |  | 4500 | 0 | ea | 0
|  | 24" Monitor |  |  | 150 | 0 | ea | 0
|  | 27" Monitor |  |  | 150 | 0 | ea | 0
|  | 27" DELL 4K monitor |  |  | 450 | 0 | ea | 0
|  | Digital Signage |  |  | 2500 | 0 | ea | 0
|  | Microsoft Surface Hub |  |  | 1500 | 0 | ea | 0
|  | Apple TV (iPad Screen Mirroring) |  |  | 70 | 0 | ea | 0
|  | Field iPad |  |  | 860 | 0 | ea | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | PROCORE |  |  | 0% | 0 | 0 | 0
|  | Procore Fee |  |  | 0.0007 | 0 | contract | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | SUFFOLK SAFETY APPLICATION |  |  | 0% | 0 | 0 | 0
|  | Safety Application - per each on site staff |  |  | 65 | #NAME? | mos | #NAME?
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | BIM 360 |  |  | 0% | 0 | 0 | 0
|  | BIM 360 |  |  | 0.00025 | 0 | contract | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | BIM |  |  | 0% | 0 | 0 | 0
|  | Scanning an Existing Building |  |  | 0.3 | 0 | sf | 0
|  | QA/QC of a New Building |  |  | 0.6 | 0 | sf | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | LEAN CONSULTING |  |  | 0% | 0 | 0 | 0
|  | Internal Consulting |  |  | #NAME? | #NAME? | mos | #NAME?
|  | Touchplan Fees, Monthly |  |  | #NAME? | #NAME? | mos | #NAME?
|  | Touchplan Fees, One Time Fee |  |  | #NAME? | 1 | lsum | #NAME?
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | MISCELLANEOUS EXPENSES |  |  | 0% | 0 | 0 | 0
|  | Suffolk Project Sign |  |  | 3000 | 1 | lsum | 3000
|  | Marketing Photographs |  |  | 2000 | 1 | lsum | 2000
|  | Aerial Photos |  |  | 0 | 1 | lsum | 0
|  | Client Entertainment |  |  | 0 | 1 | lsum | 0
|  | Association Dues - TEXO |  |  | 0 | 1 | lsum | 0
|  | Groundbreaking Ceremony |  |  | 0 | 1 | lsum | 0
|  | Topping Off Ceremony |  |  | 0 | 1 | lsum | 0
|  | Team-Building Event |  |  | 0 | 1 | lsum | 0
|  | 0 |  |  | 0% | 0 | 0 | 0
|  | GENERAL CONDITIONS TOTAL | [5 empty] | #NAME?
[7 empty] | Missing | #NAME?
Don't Forget to relocate the items below that were transferred from the GRs up into the GCs
Line Item
Header
#REF!
Phase Item
`
move on page
add blank row
delete
add line item
add header
move to GRs
  Restore Defaults
  Toggle Names
  Button Three
  Button Four

## GRs Owner (hidden)
0
General Requirements
2018-08-15 08:16
|  |  | Value | QT | Unit | TOTAL
|  | REPROGRAPHICS | 0% | 0 | 0 | 0
|  | Pre-Construction | 0 | 1 | lsum | 0
|  | Construction | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | POSTAGE & COURIER | 0% | 0 | 0 | 0
|  | Pre-Construction | 0 | 1 | lsum | 0
|  | Construction | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | EXPLORITORY & SURVEYING SERVICES | 0% | 0 | 0 | 0
|  | Exploratory Investigations | 0 | 1 | lsum | 0
|  | Surveying Equipment | 0 | 1 | lsum | 0
|  | Surveying Services | 1600 | 0 | day | 0
|  | Survey Exist. Cond. / As-Builts | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | CONSTRUCTION PARKING & TRANSPORTATION | 0% | 0 | 0 | 0
|  | Rental of Offsite Parking Lot | 0 | 1 | lsum | 0
|  | Parking Shuttle Van | 0 | 1 | lsum | 0
|  | Parking Shuttle Van Driver | 280 | 0 | day | 0
|  | 0 | 0% | 0 | 0 | 0
|  | CONSULTING SERVICES | 0% | 0 | 0 | 0
|  | Misc. Consulting Services | 0 | 1 | lsum | 0
|  | Envelope Consulting Services | 0 | 1 | lsum | 0
|  | Structural Consulting Services | 0 | 1 | lsum | 0
|  | Equipment Consulting Services | 0 | 1 | lsum | 0
|  | Minority / HUB Consulting Services | 0 | 1 | lsum | 0
|  | LEED / Dallas Green Consulting Services | 0 | 1 | lsum | 0
|  | Legal Services | 0 | 1 | lsum | 0
|  | Smoke Control | 0 | 1 | lsum | 0
|  | Small Business/Work Force Compliance Consultant | 0 | 1 | lsum | 0
|  | Lean Consulting Services | 0 | 1 | lsum | 0
|  | Partnering Session | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | MISCELLANEOUS SUPPORT & EQUIPMENT | 0% | 0 | 0 | 0
|  | Mock Ups (include removal) | 0 | 1 | lsum | 0
|  | SkyTrak | 0 | 1 | lsum | 0
|  | Forklift | 0 | 1 | lsum | 0
|  | Scissor Lift | 0 | 1 | lsum | 0
|  | Teamster | 5000 | 0 | wks | 0
|  | Trucking/Transportation | 0 | 1 | lsum | 0
|  | Storage Trailer | 165 | #NAME? | mos | #NAME?
|  | Master Mechanic | 6000 | 0 | wks | 0
|  | Tools & Equipment | 1000 | #NAME? | mos | #NAME?
|  | Radios | 0 | 0 | ea | 0
|  | Rodent Control | 300 | 0 | mos | 0
|  | Mock Ups (include removal) | 0 | 1 | lsum | 0
|  | Off Hours Work Permit | 100 | 0 | days | 0
|  | Punch List | 0 | 1 | lsum | 0
|  | Cut & Patch | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | WATER CONSUMPTION | 0% | 0 | 0 | 0
|  | Water Consumption | 0 | #NAME? | mos | #NAME?
|  | 0 | 0% | 0 | 0 | 0
|  | ELECTRICITY CONSUMPTION | 0% | 0 | 0 | 0
|  | Electric Consumption | 0 | #NAME? | mos | #NAME?
|  | Temp. Electric Vault & Service | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | TEMPORARY TOILETS | 0% | 0 | 0 | 0
|  | Portables | 0 | 0 | ea | 0
|  | Portable Unit Delivery Fee | 0 | 1 | lsum | 0
|  | Temp Bathroom Install | 100 | 0 | ea | 0
|  | Temp Bathroom Remove | 100 | 0 | ea | 0
|  | Temp Bathroom Cleaning | 0 | #NAME? | wks | #NAME?
|  | Hand Sanitizer | 0 | 0 | ea | 0
|  | Hand Wash Stations | 0 | 0 | ea | 0
|  | Gel Pak | 0 | 0 | ea | 0
|  | Holding Tanks | 0 | 0 | ea | 0
|  | 0 | 0% | 0 | 0 | 0
|  | CONSTRUCTION MANAGEMENT PLAN | 0% | 0 | 0 | 0
|  | Sidewalk Bridge | 175 | 0 | lf | 0
|  | New Traffic Markings | 0 | 1 | lsum | 0
|  | Remove Old/Existing Traffic Markings | 0 | 1 | lsum | 0
|  | Temporary Road Signs | 0 | 1 | lsum | 0
|  | Sidewalk Rental | 0 | #NAME? | mos | #NAME?
|  | Street Rental | 0 | #NAME? | mos | #NAME?
|  | Covered Pedestrian Walkways | 0 | #NAME? | mos | #NAME?
|  | Car Washes | 0 | 1 | lsum | 0
|  | Turnstiles | 0 | 1 | lsum | 0
|  | Guard Shack/s | 0 | 1 | lsum | 0
|  | Security | 0 | #NAME? | mos | #NAME?
|  | Site Security System | 0 | #NAME? | mos | #NAME?
|  | Progress Photos | 0 | 1 | lsum | 0
|  | Aerial Photos | 0 | 1 | lsum | 0
|  | MultiVista | 0 | 1 | lsum | 0
|  | Railway Spotter | 0 | #NAME? | mos | #NAME?
|  | Car/Boat Detailing | 0 | 1 | lsum | 0
|  | Clean Adjacent Building | 0 | 1 | lsum | 0
|  | MOT Plan | 0 | 1 | lsum | 0
|  | Miscellaneous Permits | 0 | 1 | lsum | 0
|  | Overtime Inspection Costs | 0 | 1 | lsum | 0
|  | Access Point Turnstiles | 0 | 1 | lsum | 0
|  | Hurricane Preparation | 0 | 1 | lsum | 0
|  | Parking Meter Fees | 0 | #NAME? | mos | #NAME?
|  | Off Hours Permit | 100 | 0 | events | 0
|  | 0 | 0% | 0 | 0 | 0
|  | CONSTRUCTION FENCE | 0% | 0 | 0 | 0
|  | Jersey Barriers | 12 | 0 | lf/month | 0
|  | Fence on top of Jersey Barriers | 10 | 0 | lf | 0
|  | Chain Link Fence | 18 | 0 | lf | 0
|  | Windscreen/Scrim/Red Ribbon | 0 | 0 | lf | 0
|  | Water Barriers | 0 | 0 | lf | 0
|  | Gates | 500 | 0 | ea | 0
|  | Maintenance & Relocations | 0 | #NAME? | wks | #NAME?
|  | Fence Removal | 0 | 0 | lf | 0
|  | Laborer to Open & Close Gates | 0 | 0 | hrs | 0
|  | 0 | 0% | 0 | 0 | 0
|  | SAFETY SUPPLIES & EQUIPMENT | 0% | 0 | 0 | 0
|  | Temporary Fire Extinguishers & Stands | 200 | 0 | ea | 0
|  | Temporary Signage | 0 | 1 | lsum | 0
|  | First Aid Supplies | 0 | #NAME? | mos | #NAME?
|  | Shanty Protection - smoke detector & fire extinguisher | 200 | 0 | ea | 0
|  | Shanty Protection - NYC Sprinkler Kit (not required yet - over 40 stories only) | 750 | 0 | ea | 0
|  | Fire Department Post (signage, gang box, keys, plans, etc. - over 40 stories only) | 5000 | 0 | ea | 0
|  | Creation of Temp. Fire Protection Plan (over 40 stories only) | 25000 | 0 | ea | 0
|  | Misc. Safety Supplies (hard hats, safety glasses, harnesses, etc) | 0 | #NAME? | mos | #NAME?
|  | 0 | 0% | 0 | 0 | 0
|  | MISC LABOR & CLEANING | 0% | 0 | 0 | 0
|  | Materials | 0 | #NAME? | mos | #NAME?
|  | Cleaning Supplies | 0 | #NAME? | mos | #NAME?
|  | Cleaning Site | 0 | 0 | hrs | 0
|  | Cleaning Trailers/Office | 0 | 0 | hrs | 0
|  | Rubbish Chute | 2000 | 0 | floors | 0
|  | Waste Management Plan | 2000 | 1 | lsum | 2000
|  | Final Cleaning - Building | 0 | 0 | sf | 0
|  | Final Cleaning - Parking | 0 | 0 | sf | 0
|  | Final Clean - Exterior Windows | 0 | 0 | sf | 0
|  | Pre-Clean - Exterior Windows | 0 | 0 | sf | 0
|  | Final Clean - Interiors | 0 | 0 | sf | 0
|  | Pre-Clean - Interiors | 0 | 0 | sf | 0
|  | 0 | 0% | 0 | 0 | 0
|  | TEMPORARY SAFETY & PROTECTION | 0% | 0 | 0 | 0
|  | Materials | 0 | 0 | lsum | 0
|  | Temporary Stairs | 0 | 0 | ea | 0
|  | Perimeter Fall Protection | 0 | 0 | lsum | 0
|  | Elevator Protection | 0 | 0 | lsum | 0
|  | Floor Protection | 0 | 0 | lsum | 0
|  | Door Protection | 0 | 0 | lsum | 0
|  | Window Protection | 0 | 0 | lsum | 0
|  | Temporary Wall Protection | 0 | 0 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | DUMPSTERS | 0% | 0 | 0 | 0
|  | Dumpsters | 650 | 0 | loads | 0
|  | Recycle Dumpster Premium | 0 | 1 | lsum | 0
|  | Post-Sort Services | 0 | 1 | lsum | 0
|  | Overweight Pulls (10% of total # of loads) | 100 | 0 | loads | 0
|  | 0 | 0% | 0 | 0 | 0
|  | PERSONNEL & MATERIAL HOISTING | 0% | 0 | 0 | 0
|  | Mobilize, Erect & Dismantle | 0 | 0 | lsum | 0
|  | Police Details, Cranes, Permits during E & D | 0 | 0 | lsum | 0
|  | Operating Engineers during E & D | 0 | 0 | lsum | 0
|  | Hoist Rental (Single Car) | 0 | #NAME? | mos | #NAME?
|  | Hoist Rental (Double Car) | 0 | #NAME? | mos | #NAME?
|  | Gate Rental | 0 | #NAME? | mos | #NAME?
|  | Gate Installation | 0 | 0 | lsum | 0
|  | Hoist Rental Insurance | 0 | 0 | lsum | 0
|  | Communication Boxes | 0 | #NAME? | mos | #NAME?
|  | Jumps | 0 | 0 | ea | 0
|  | Sales Tax | 0 | 0 | ea | 0
|  | Operator Car #1 (Regular Time) | 0 | #NAME? | wks | #NAME?
|  | Operator Car #2 (Regular Time) | 0 | #NAME? | wks | #NAME?
|  | Operator Car #1 (Overtime) | 0 | #NAME? | wks | #NAME?
|  | Operator Car #2 (Overtime) | 0 | #NAME? | wks | #NAME?
|  | Temporary Interior Elevator Operator (Regular Time) | 0 | #NAME? | wks | #NAME?
|  | Temporary Interior Elevator Operator (Overtime) | 0 | #NAME? | wks | #NAME?
|  | Overtime Equipment Hours | 0 | 0 | hrs | 0
|  | Elevator Maintenance | 0 | #NAME? | mos | #NAME?
|  | Elevator Repairs | 0 | 1 | lsum | 0
|  | Drop Tests | 0 | 1 | lsum | 0
|  | Fence Enclosures | 0 | 0 | ea | 0
|  | Concrete Pad | 0 | 0 | ea | 0
|  | Reinforce Existing Structure @ Tie-Ins | 0 | 0 | ea | 0
|  | Loading Docks/Ramps/Overhead Prot. | 0 | 0 | ea | 0
|  | Cab Protection | 0 | 1 | lsum | 0
|  | Plywood Partitions @ Gates | 0 | 0 | ea | 0
|  | Temporary Power Consumption | 0 | 0 | ea | 0
|  | Temporary Power Service | 0 | #NAME? | mos | #NAME?
|  | Threshold Rentals | 0 | #NAME? | mos | #NAME?
|  | Assist Crane | 0 | #NAME? | mos | #NAME?
|  | 3rd Party Certification | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | WINTER CONDITIONS / TEMPORARY HEAT | 0% | 0 | 0 | 0
|  | Temporary Heating | 0 | 1 | lsum | 0
|  | Temporary Cooling | 0 | 1 | lsum | 0
|  | Temporary De-Humidification | 0 | 1 | lsum | 0
|  | Negative Air Machines | 0 | 0 | ea | 0
|  | Dewatering | 0 | 1 | lsum | 0
|  | Snow Removal from Building | 0 | 1 | lsum | 0
|  | Snow Removal from Site | 0 | 1 | lsum | 0
|  | Temporary Construction | 0 | 1 | lsum | 0
|  | Miscellaneous Heat & Tarps | 0 | 0 | mos | 0
|  | Portable Heaters | 0 | 0 | mos | 0
|  | Babfar Rental/Install | 0 | 0 | mos | 0
|  | Temp. Ductwork | 0 | 1 | lsum | 0
|  | Use/cln perm.system | 0 | 0 | mos | 0
|  | Fuel | 0 | 0 | wks | 0
|  | 0 | 0% | 0 | 0 | 0
|  | STAGING & SCAFFOLDING | 0% | 0 | 0 | 0
|  | Exterior Scaffolding first months rental & dismantle | 0 | 0 | ea | 0
|  | Exterior Scaffolding monthly rental | 0 | 0 | mos | 0
|  | Exterior Scaffolding move planks | 0 | 0 | days | 0
|  | Interior Scaffolding first months rental & dismantle | 0 | 0 | ea | 0
|  | Interior Scaffolding monthly rental | 0 | 0 | mos | 0
|  | Interior Scaffolding move planks | 0 | 0 | days | 0
|  | 0 | 0% | 0 | 0 | 0
|  | TESTING & INSPECTIONS | 0% | 0 | 0 | 0
|  | Soils | 0 | 0 | ea | 0
|  | Concrete | 0 | 0 | ea | 0
|  | Steel | 0 | 0 | ea | 0
|  | Spray Fireproofing | 0 | 0 | ea | 0
|  | Curtainwall & Windows | 0 | 0 | ea | 0
|  | 0 | 0% | 0 | 0 | 0
|  | LABOR ITEMS | 0% | 0 | 0 | 0
|  | Clean-Up Labor | 0 | 1 | lsum | 0
|  | Safety (C & L) | 0 | 1 | lsum | 0
|  | Police | 0 | 1 | lsum | 0
|  | Labor Steward | 0 | 1 | lsum | 0
|  | Carpenter Steward | 0 | 1 | lsum | 0
|  | Fire Watch | 0 | 1 | lsum | 0
|  | 0 | 0% | 0 | 0 | 0
|  | 0 | 0% | 0 | 0 | 0
|  | GENERAL REQUIREMENTS TOTAL |  |  |  | #NAME?
[5 empty] | Missing | #NAME?
Don't Forget to relocate the items below that were transferred from the GRs up into the GCs
Line Item
Header
#REF!
move on page
add blank row
delete
add line item
add header
move to GCs
`
  Restore Defaults
  Button Two
  Button Three
  Button Four

## Bin (hidden)
CLEANING & MISC. LABOR |  |  |  | #REF! | [
Clean-up Laborers | 1 | lsum | #REF! | #REF! | 1
Laborers |  | lsum |  | 0 | 1
Materials |  | mos |  | 0 | 1
Cleaning Supplies |  | wks |  | 0 | 1
Cleaning Site |  | hrs |  | 0 | 1
Cleaning Trailers/Office | 1 | hrs | 0 | 0 | 1
TEMPORARY SAFETY & PROTECTION |  |  |  | #REF! | [
Carpenters | 1 | lsum |  | 0 | 1
Laborers | 1 | lsum | #REF! | #REF! | 1
Materials |  | lsum | 0 | 0 | 1
Stair Towers during excavation of foundation |  | ea | 0 | 0 | 1
1

## Errors (hidden)
USERNAME | MODULE | PROCEDURE | MESSAGE | NUMBER | TIME

## Code (hidden)
| \position | \rank | \order | \salary | \auto | \revit | \id |  | copiers |  |  | institutional BIM |  |  | Commercial BIM |  |  | Trailers | [11 empty] | GCGR_TemplateNEWPENDING.xlsx
| Position | Rank | Insert Order | Salary Default | Auto | Tokens/wk | ID |  | if >= | then |  | if >= | then |  | if >= | then |  |  | (60 x 12) Single-wide trailer | (64 x 24) Double-wide trailer | (64 x 36) Triple-wide trailer |  | Trailer Table
| VP Of Operations | 6 | 1.2 | 336200 | 12000 | 0 |  |  | 0 | 2000 |  | 0 | 0 |  | 0 | 0 |  | Rent | 400 | 1125 | 2450 |  | (60 x 12) Single-wide trailer
| Project Executive 3 | 4 | 1.25 | [5 empty] | 5 | 7500 |  | 3000000 | 10000 |  | 3000000 | 10000 |  | Delivery | 7700 | 21500 | 28500 |  | (64 x 24) Double-wide trailer
| Project Executive 2 | 4 | 1.3 | 277840 | 9000 | 2 |  |  | 10 | 12500 |  | 10000000 | 40000 |  | 10000000 | 50000 |  | Pick-up | 5000 | 16500 | 21000 |  | (64 x 36) Triple-wide trailer
| Project Executive 1 | 4 | 1.4 | 215860 | 8000 | 2 | [5 empty] | 50000000 | 100000 |  | 50000000 | 220000 |  | Aluminum Steps | 50 | 50 | 50
| Sr. Project Manager 2 | 1 | 1.5 | 201170 | 7200 | 2 | [5 empty] | 150000000 | 200000 |  | 250000000 | 380000 |  | Security System | 50 | 50 | 50
| Sr. Project Manager 1 | 4 | 1.6 | 165570 | 6800 | 2 |  |  | internet |  |  | 300000000 | 400000 |  | 450000000 | 550000 |  | Utility Connections | 2000 | 2000 | 2000
| Project Manager 2 | 4 | 2.2 | 154810 | 6000 | 0 |  |  | if >= | then | [7 empty] | Utility Consumption | 100 | 200 | 300
| Project Manager 1 | 10 | 2.2 | 115240 | 6000 | 0 |  |  | 0 | 800 | [7 empty] | Skirting
| Asst Project Manager 1 | 10 | 2.3 | 77210 |  | 2 |  |  | 5 | 1600
| Asst Project Manager 2 | 2 | 2.4 | 95800 |  | 3 |  |  | 15 | 2000
| Project Engineer | 2 | 2.5 | 70000 |  | 5
| Proj Admin | 5 | 2.6 | 62750 |  | 5
| General Superintendent | 3 | 2.7 | 348880 | 12000 | 3 |  |  | Internal Consulting |  |  | touchplan fees | [5 empty] | Labor |  |  |  |  | Schedule Table
| Sr. Superintendent 3 | 10 | 2.8 | 286640 | 9000 | 3 |  |  | if >= | then |  | if >= | monthly | one time |  |  |  | if >= | Straight | 1-1/2X | 2X |  | Boston | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Sr. Superintendent 2 | 5 | 2.9 | 226300 | 8000 | 0 |  |  | 0 | 0 |  | 0 | 550 | 1000 |  |  | 0 | 0 |  |  |  |  | New York | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Sr. Superintendent 1 | 2 | 3.2 | 185620 | 7200 | 0 |  |  | 5000000 | 250 |  | 10000000 | 750 | 1500 |  |  |  | 1900-06-30 |  |  |  |  | Miami | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 3 | 4 | 3.3 | 181330 | 7200 | 0 |  |  | 25000000 | 400 |  | 100000000 | 1250 | 2500 |  |  |  | 1900-12-29 |  |  |  |  | West Palm Beach | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 2 | 7 | 3.4 | 151260 | 6000 | 0 |  |  | 100000000 | 600 | [7 empty] | 1901-06-29 |  |  |  |  | Estero | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Superintendent 1 | 8 | 4.1 | 122400 | 6000 | 0 | [11 empty] | 1901-12-28 |  |  |  |  | Tampa | Miscelleneous Labor | Safety (C & L) | Flagman | Labor Steward | Carpenters | KeyRunner
| Asst Superintendent 2 | 9 | 4.2 | 95200 |  | 0 | [11 empty] | 1902-06-28 |  |  |  |  | Dallas | Clean-Up Labor | Safety & Carpentry | Police | Labor Steward | Carpenter Steward | Fire Watch
| Asst Superintendent 1 |  | 4.3 | 80420 | [13 empty] | 1902-12-27 |  |  |  |  | San Diego | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| MEP Superintendent |  | 4.35 | [5 empty] | Labor Rates | [13 empty] | Los Angeles | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| Director Of Field Ops |  | 4.38 | [6 empty] | RT | OT | DT | [10 empty] | San Francisco | Clean-Up Labor | Safety & Carpentry | Flagman | Labor Steward | Carpenter Steward | Fire Watch
| Field Engineer |  | 4.4 | 70000 |  |  |  |  | Boston | 100 | 130
| Senior Safety Manager 1 |  | 4.45 | [5 empty] | New York
| Safety Manager 2 |  | 4.5 | 135170 | 7200 |  |  |  | Miami | [6 empty] | (60 x 12) Single-wide trailer
| Safety Manager 1 |  | 4.6 | 92050 |  |  |  |  | West Palm Beach | [6 empty] | Rent
| Reg Safety Director |  | 4.7 | 175090 | 7200 |  |  |  | Estero |  |  |  | 10000000
| Scheduling Director (601) |  | 4.8 | 233970 |  |  |  |  | Tampa
| Senior Scheduler |  | 4.9 | 160100 |  |  |  |  | Dallas | [8 empty] | Boston | New York | Miami | West Palm Beach | Estero | Tampa | Dallas | San Diego | Los Angeles | San Francisco
| Scheduler |  | 5 | 96760 |  |  |  |  | San Diego | [5 empty] | OT ratio: | 1.27 | 40 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Junior Scheduler |  | 5.05 | [5 empty] | Los Angeles | [5 empty] | DT Ratio: | 1.5 | 50 | 1.054 | 1.1 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25
| VP Engineering |  | 5.1 | 297030 | 12000 |  |  |  | San Francisco | [7 empty] | 60 | 1.09 | 1.17 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Sr. MEP Project Manager |  | 5.2 | 202150 | 8000
| MEP Project Manager |  | 5.3 | 154020
| Reg. BIM/VDC Director |  | 5.4 | 200000 | 7200
| VDC Manager |  | 5.5 | 130540
| VDC Coordinator |  | 5.6 | 77730
| Director of Trade Partner Diversity |  | 5.7 | 149760
| Trade Partner Diversity Officer |  | 5.8 | 68660
| Project Controller |  | 5.9 | 129280
| Project Accountant |  | 6 | 68450
| VP of Preconstruction |  | 6.1 | 360850 | 12000
\est | Chief Estimator |  | 6.15 |  |  |  | est
\est | Sr. Estimator 2 |  | 6.2 | 259220 |  |  | est
\est | Sr. Estimator 1 |  | 6.3 | 197980 |  |  | est
\est | MEP Estimator |  | 6.4 | 211440 |  |  | est
\est | Estimator 2 |  | 6.5 | 150790 |  |  | est
\est | Estimator 1 |  | 6.55 |  |  |  | est
\est | Estimating Manager |  | 6.57 |  |  |  | est
\est | Assistant Estimator |  | 6.6 | 85430 |  |  | est
\est | Estimating Assistant |  | 6.7 | 75920 |  |  | est
\est | Career Start Estimator |  | 6.9 | 70000 |  |  | est
| Intern |  | 7
| Safety Presets | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| if >= | Boston | New York | Miami | West Palm Beach | Estero | Tampa | Dallas | San Diego | Los Angeles | San Francisco
| 0 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 |  |  |  |  | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1
| 5000000 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1 | \safety, 1, 0.5;\srsafety, 1, 0.1
| 40000000 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 |  |  |  |  | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2 | \safety, 1, 1;\srsafety, 1, 0.2
| 150000000 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 |  |  |  |  | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35 | \safety, 2, 1;\srsafety, 1, 0.35

## CostCodes (hidden)
Code | Cost Code Description | MF3 | Map Description
010000.000 | General Requirements | 10000 | General Requirements
010100.010 | Document Reproduction | 10000 | Document Reproduction
010100.015 | Postage and Courier | 10000 | Postage and Courier
010100.020 | Exploratory Investigations | 10000 | Exploratory Investigations
010100.030 | Surveying Equipment | 10000 | Surveying Equipment
010100.040 | Surveying Services | 10000 | Surveying Services
010100.050 | Survey Exist. Cond. / As-Builts | 10000 | Survey Exist. Cond. / As-Builts
010100.060 | Parking Shuttle Van | 10000 | Parking Shuttle Van
010100.070 | Parking Shuttle Van Driver | 10000 | Parking Shuttle Van Driver
010100.080 | Consulting Services | 10000 | Consulting Services
010100.090 | Partnering Sessions | 10000 | Partnering Sessions
010100.100 | Entertainment / Topping Off / Etc. | 10000 | Entertainment / Topping Off / Etc.
010100.110 | Master Mechanic | 10000 | Master Mechanic
010100.120 | Teamster | 10000 | Teamster
010100.130 | Trucking/Transportation | 10000 | Trucking/Transportation
010100.140 | On Site Vehicle | 10000 | On Site Vehicle
010100.150 | Storage Trailer | 10000 | Storage Trailer
010100.160 | Tools and Equipment | 10000 | Tools and Equipment
010100.170 | Rodent Control | 10000 | Rodent Control
010100.180 | Mock Ups (include removal) | 10000 | Mock Ups (include removal)
010100.190 | Punch List | 10000 | Punch List
010100.200 | Cut and Patch | 10000 | Cut and Patch
010100.210 | Signage | 10000 | Signage
010100.215 | Digital Signage | 10000 | Digital Signage
010100.220 | Smart Box | 10000 | Smart Box
010100.230 | Owner Office Trailers | 10000 | Owner Office Trailers
010100.235 | Office Trailer Lot Rental | 10000 | Office Trailer Lot Rental
010100.240 | Office Trailer Lot Improvements | 10000 | Office Trailer Lot Improvements
011030.020 | Precon - Misc Preconstruction Costs | 10000 | Precon - Misc Preconstruction Costs
011100.010 | Temporary Utilities | 11100 | Summary of Work
011100.020 | Temp Electricity - Consumption | 11100 | Summary of Work
011100.030 | Temp Electricity - Install Temp Vault | 11100 | Summary of Work
011100.040 | Temp Power and Light - Install | 11100 | Summary of Work
011100.050 | Temp Heating Fuel (Oil/Gas/Steam) | 11100 | Summary of Work
011100.060 | Temp Cooling | 11100 | Summary of Work
011100.070 | Temp Toilets | 11100 | Summary of Work
011100.080 | Temp Construction Water | 11100 | Summary of Work
011100.090 | Temp Sewer | 11100 | Summary of Work
011100.100 | Temp Utilities - Deposits | 11100 | Summary of Work
011200.070 | Consumables/Meals | 11200 | Multiple Contract Summary
011200.080 | Water/Coffee | 11200 | Multiple Contract Summary
012050.010 | Office Trailer | 11800 | Project Utility Sources
012050.090 | BIM | 11800 | Project Utility Sources
012070.040 | Progress Photos | 11800 | Project Utility Sources
012100.010 | Safety Labor | 12100 | Allowances
012100.020 | Safety Material and Equipment | 12100 | Allowances
012100.030 | Temp Fire Protection | 12100 | Allowances
012100.040 | Temp Railings | 12100 | Allowances
012100.050 | Police Details | 12100 | Allowances
012100.060 | Fire Watch | 12100 | Allowances
012100.065 | Fire Detail | 12100 | Allowances
012100.070 | Security/Watchman Service | 12100 | Allowances
012100.080 | Rail Road Flagmen | 12100 | Allowances
012100.090 | Temp Labor Services | 12100 | Allowances
013100.010 | Rubbish Chute | 13100 | Project Management and Coordination
013100.020 | Interim Cleaning | 13100 | Project Management and Coordination
013100.025 | Field Office Cleaning | 13100 | Project Management and Coordination
013100.030 | Final Cleaning - Building | 13100 | Project Management and Coordination
013100.040 | Final Cleaning - Parking | 13100 | Project Management and Coordination
013100.050 | Glass Cleaning | 13100 | Project Management and Coordination
013100.060 | Dumpsters | 13100 | Project Management and Coordination
013529.000 | Health, Safety, and Emergency Response Procedures | 13500 | Special Procedures
014100.010 | Temp Mobile Cranes - Use | 14100 | Regulatory Requirements
014100.020 | Temporary Tower Cranes - Install/Remove | 14100 | Regulatory Requirements
014100.030 | Temporary Tower Cranes - Use | 14100 | Regulatory Requirements
014100.040 | Temporary Tower Cranes - Power Supply | 14100 | Regulatory Requirements
014100.050 | Temporary Tower Cranes - Construct/Remove Base | 14100 | Regulatory Requirements
014100.060 | Temporary Hoists - Install/Remove | 14100 | Regulatory Requirements
014100.070 | Temporary Hoists - Use | 14100 | Regulatory Requirements
014100.075 | Temporary Hoists - Operator | 14100 | Regulatory Requirements
014100.080 | Temporary Hoists - Loading Platform | 14100 | Regulatory Requirements
014100.090 | Temporary Scaffolding and Platforms | 14100 | Regulatory Requirements
014100.100 | Temporary Swing Staging | 14100 | Regulatory Requirements
014100.110 | Temporary Elevators - Protect Finished Cabs | 14100 | Regulatory Requirements
014100.120 | Temporary Elevators - Operator | 14100 | Regulatory Requirements
014100.130 | Trucking | 14100 | Regulatory Requirements
015100.010 | Temp Access Roads | 15100 | Temporary Utilities
015100.020 | Temp Parking Areas | 15100 | Temporary Utilities
015100.030 | Traffic Control | 15100 | Temporary Utilities
015100.040 | Street / Sidewalk Permits | 15100 | Temporary Utilities
015100.050 | Parking Meter Rental | 15100 | Temporary Utilities
015100.060 | Sidewalk/Parking Lane Deposit | 15100 | Temporary Utilities
015100.070 | Permits | 15100 | Temporary Utilities
016100.010 | Temporary Air Barriers | 16100 | Common Product Requirements
016100.020 | Temporary Dust Barriers | 16100 | Common Product Requirements
016100.030 | Temporary Noise Barriers | 16100 | Common Product Requirements
016100.040 | Temporary Barricades | 16100 | Common Product Requirements
016100.050 | Temporary Fencing | 16100 | Common Product Requirements
016100.060 | Temporary Protective Walkways | 16100 | Common Product Requirements
016100.070 | Temporary Security Barriers | 16100 | Common Product Requirements
016100.080 | Temporary Security Enclosures | 16100 | Common Product Requirements
016100.090 | Temporary Tree and Plant Protection | 16100 | Common Product Requirements
016100.100 | Scrim/Screens | 16100 | Common Product Requirements
016100.110 | Move Fencing | 16100 | Common Product Requirements
017100.010 | Winter Conditions - Fuel | 17100 | Examination and Preparation
017100.020 | Winter Conditions - Heaters | 17100 | Examination and Preparation
017100.030 | Winter Conditions - Enclosures | 17100 | Examination and Preparation
017100.040 | Winter Conditions - Winter Concrete | 17100 | Examination and Preparation
017100.050 | Winter Conditions - Snow Removal | 17100 | Examination and Preparation
017100.060 | Winter Conditions - Other | 17100 | Examination and Preparation
017400.000 | Cleaning and Waste Management | 17400 | Cleaning and Waste Management
017413.000 | Progress Cleaning | 17400 | Cleaning and Waste Management
017416.000 | Site Maintenance | 17400 | Cleaning and Waste Management
017420.000 | Dust Control | 17400 | Cleaning and Waste Management
017423.000 | Final Cleaning | 17400 | Cleaning and Waste Management
017427.000 | Construction Entrance Maintenance | 17400 | Cleaning and Waste Management
018100.010 | Legal | 18100 | Facility Performance Requirements
018100.020 | Structural | 18100 | Facility Performance Requirements
018100.030 | Roofing | 18100 | Facility Performance Requirements
018100.040 | Waterproofing | 18100 | Facility Performance Requirements
018100.050 | Specialty | 18100 | Facility Performance Requirements
018100.060 | Testing and Inspection | 18100 | Facility Performance Requirements
018100.070 | Scheduling | 18100 | Facility Performance Requirements
018100.075 | Pull Planning | 18100 | Facility Performance Requirements
018100.080 | Computer/Technology | 18100 | Facility Performance Requirements
018100.085 | Construction Cameras | 18100 | Facility Performance Requirements
019100.010 | Suffolk Signage | 19100 | Commissioning
019100.020 | Temp Owner Project Signage | 19100 | Commissioning
019100.030 | Core Boards | 19100 | Commissioning
019999.000 | General Requirements Allocation | 19400 | Facility Decommissioning
019999.999 | General Requirements - Fee Contingency | 19400 | Facility Decommissioning
980000.000 | General Conditions | 980000 | General Conditions
980100.190 | Punch List | 980000 | Punch List
981000.000 | Preconstruction | 980000 | Preconstruction
981010.010 | Precon - Director of Precon | 980000 | Precon - Director of Precon
981010.020 | Precon - Chief Estimator | 980000 | Precon - Chief Estimator
981010.030 | Precon - Preconstruction Manager | 980000 | Precon - Preconstruction Manager
981010.040 | Precon - Sr. Estimator | 980000 | Precon - Sr. Estimator
981010.050 | Precon - Estimator | 980000 | Precon - Estimator
981010.060 | Precon - MEP Estimator | 980000 | Precon - MEP Estimator
981010.070 | Precon - Regional Scheduling Director | 980000 | Precon - Regional Scheduling Director
981010.080 | Precon - Scheduling Engineer | 980000 | Precon - Scheduling Engineer
981010.090 | Precon - Engineering Manager | 980000 | Precon - Engineering Manager
981010.100 | Precon - Regional BIM/VDC Director | 980000 | Precon - Regional BIM/VDC Director
981010.110 | Precon - BIM/VDC Manager | 980000 | Precon - BIM/VDC Manager
981010.120 | Precon - Purchasing Manager | 980000 | Precon - Purchasing Manager
981010.130 | Precon - Project Executive | 980000 | Precon - Project Executive
981010.140 | Precon - Senior Project Manager | 980000 | Precon - Senior Project Manager
981010.150 | Precon - Project Manager | 980000 | Precon - Project Manager
981010.160 | Precon - Assistant Project Manager | 980000 | Precon - Assistant Project Manager
981010.170 | Precon - General Superintendent | 980000 | Precon - General Superintendent
981010.180 | Precon - Senior Superintendent | 980000 | Precon - Senior Superintendent
981010.190 | Precon - Superintendent | 980000 | Precon - Superintendent
981030.010 | Precon - Prints and Copies | 980000 | Precon - Prints and Copies
981030.020 | Precon - Misc Preconstruction Costs | 980000 | Precon - Misc Preconstruction Costs
981100.080 | Temp Construction Water | 981100 | Preconstruction Staffing
982010.010 | Director of Field Ops | 981200 | Preconstruction Expenses
982010.020 | VP Operations | 981200 | Preconstruction Expenses
982010.030 | Regional Safety Director | 981200 | Preconstruction Expenses
982010.040 | Regional Scheduling Director | 981200 | Preconstruction Expenses
982010.050 | Scheduling Engineer | 981200 | Preconstruction Expenses
982010.060 | Regional Engineering Director | 981200 | Preconstruction Expenses
982010.070 | Sr. Engineering | 981200 | Preconstruction Expenses
982010.080 | Engineering Manager | 981200 | Preconstruction Expenses
982010.090 | Regional BIM/VDC Director | 981200 | Preconstruction Expenses
982010.100 | BIM/VDC Manager | 981200 | Preconstruction Expenses
982010.110 | BIM/VDC Coordinator | 981200 | Preconstruction Expenses
982010.120 | BIM/VDC Operator | 981200 | Preconstruction Expenses
982010.130 | Director of Precon | 981200 | Preconstruction Expenses
982010.140 | Chief Estimator | 981200 | Preconstruction Expenses
982010.150 | Preconstruction Manager | 981200 | Preconstruction Expenses
982010.160 | Sr. Estimator | 981200 | Preconstruction Expenses
982010.170 | Estimator | 981200 | Preconstruction Expenses
982010.180 | MEP Estimator | 981200 | Preconstruction Expenses
982010.190 | Purchasing Manager | 981200 | Preconstruction Expenses
982010.200 | Project Accountant | 981200 | Preconstruction Expenses
982010.210 | Project Controller | 981200 | Preconstruction Expenses
982010.220 | Compliance | 981200 | Preconstruction Expenses
982010.225 | Compliance Director | 981200 | Preconstruction Expenses
982010.230 | Quality Control Manager | 981200 | Preconstruction Expenses
982010.240 | Project Executive | 981200 | Preconstruction Expenses
982010.250 | Senior Project Manager | 981200 | Preconstruction Expenses
982010.260 | Project Manager | 981200 | Preconstruction Expenses
982010.270 | Assistant Project Manager | 981200 | Preconstruction Expenses
982010.280 | MEP Project Manager | 981200 | Preconstruction Expenses
982010.290 | Project Engineer (Office) | 981200 | Preconstruction Expenses
982010.300 | Administrative Assistant | 981200 | Preconstruction Expenses
982010.310 | General Superintendent | 981200 | Preconstruction Expenses
982010.320 | Senior Superintendent | 981200 | Preconstruction Expenses
982010.330 | Superintendent | 981200 | Preconstruction Expenses
982010.340 | Assistant Superintendent | 981200 | Preconstruction Expenses
982010.350 | Safety Manager | 981200 | Preconstruction Expenses
982010.360 | Project Engineer (Field) | 981200 | Preconstruction Expenses
982010.370 | Insurance Admin | 981200 | Preconstruction Expenses
982010.380 | Intern/Career Start | 981200 | Preconstruction Expenses
982010.900 | Labor Increases | 981200 | Preconstruction Expenses
982030.010 | Weekly Parking Fees | 981200 | Preconstruction Expenses
982030.020 | Recruiting Charges | 981200 | Preconstruction Expenses
982030.025 | Travel | 981200 | Preconstruction Expenses
982030.030 | Mileage | 981200 | Preconstruction Expenses
982030.040 | Airfare | 981200 | Preconstruction Expenses
982030.050 | Hotel | 981200 | Preconstruction Expenses
982030.060 | Car Rental | 981200 | Preconstruction Expenses
982030.070 | House/Apartment Rental | 981200 | Preconstruction Expenses
982030.080 | Tolls | 981200 | Preconstruction Expenses
982030.090 | Food Allowance | 981200 | Preconstruction Expenses
982030.100 | Vehicle Fuel | 981200 | Preconstruction Expenses
982050.010 | Office Trailer | 981200 | Preconstruction Expenses
982050.020 | Office Furniture and Equipment | 981200 | Preconstruction Expenses
982050.025 | Office Other | 981200 | Preconstruction Expenses
982050.030 | Communications | 981200 | Preconstruction Expenses
982050.040 | Computer Equipment | 981200 | Preconstruction Expenses
982050.045 | Procore | 981200 | Preconstruction Expenses
982050.050 | On Trac | 981200 | Preconstruction Expenses
982050.060 | DBO2 | 981200 | Preconstruction Expenses
982050.070 | Vela | 981200 | Preconstruction Expenses
982050.080 | Misc. Software | 981200 | Preconstruction Expenses
982050.085 | LGB Tracker | 981200 | Preconstruction Expenses
982050.090 | BIM | 981200 | Preconstruction Expenses
982050.095 | Radios | 981200 | Preconstruction Expenses
982050.100 | Cell Phones | 981200 | Preconstruction Expenses
982050.110 | Field Internet Communications | 981200 | Preconstruction Expenses
982070.010 | Suffolk Signage | 981200 | Preconstruction Expenses
982070.020 | Postage and Courier | 981200 | Preconstruction Expenses
982070.030 | Marketing Photographs | 981200 | Preconstruction Expenses
982070.040 | Progress Photos | 981200 | Preconstruction Expenses
982070.050 | Office Supplies | 981200 | Preconstruction Expenses
982070.060 | Permits | 981200 | Preconstruction Expenses
982070.070 | Prints and Copies | 981200 | Preconstruction Expenses
982080.010 | Owner Office Trailer | 981200 | Preconstruction Expenses
982080.020 | Owner Office Furniture and Equip. | 981200 | Preconstruction Expenses
982080.030 | Owner IT and Support Charges | 981200 | Preconstruction Expenses
982080.040 | Security/Watchman Service | 981200 | Preconstruction Expenses
983010.000 | Storage Trailer | 982500 | Owner Support
983020.000 | Tools and Equipment | 982500 | Owner Support
983030.000 | Safety Material and Equipment | 982500 | Owner Support
983050.010 | Safety Allocation | 982500 | Owner Support
983050.020 | Lean Allocation | 982500 | Owner Support
984100.010 | Temp Toilets | 982500 | Owner Support
984100.020 | Dumpsters | 982500 | Owner Support
989000.000 | Warranty | 982500 | Owner Support
989999.000 | General Conditions Allocation | 982500 | Owner Support
989999.999 | General Conditions - Fee Contingency | 982500 | Owner Support

## splash (hidden)
dataSMART GCs & GRs
MACROS MUST BE ENABLED TO USE THIS WORKBOOK
Close this workbook and reopen. When this workbook opens, select 'ENABLE' when prompted.
If you do not see a prompt to enable Macros, follow the below steps:
[1] Click the 'File' tab in the menu header above
[2] Select 'Options' in the navigation bar on the left
[3] Select 'Trust Center' in the left navigation bar
[4] Click the 'Trust Center Settings' button on the middle right
[5] Under the Macro Settings header, click 'Disable all macros with notification'
[6] Close this workbook and excel, select 'ENABLE' when prompted
Click Anywhere For Startup